## Overview
Clair — Project & Task Report
Generated 27/8/2026, 4:55:10 pm
16 | 189 | 13 | 7 | 2020
Projects | Tasks | Releases | Release Points | Test Cases
Applied Filters
Projects | All Projects
Developers | All Developers
Date Range | 2026-04-06 to 2026-08-27
Task Status | All Statuses
Release Status | All Statuses
Test Case Status | All Statuses
Category Breakdown
Projects |  |  |  | 16
Tasks (in scope) |  |  |  | 189
Releases |  |  |  | 13
Release Points |  |  |  | 7
Test Cases |  |  |  | 2020

## Projects
# | Project Name | Type | Current Status | Version (Prev → Upcoming) | Past Released Versions | Completed Tasks | Total Tasks
1 | CIMTrack Dashboard | Web | Testing, Issue Assigned, New Development | v1.6 → v1.7 | WEB v1.6 (11 Aug 2026) | 30 | 31
2 | CIMTrack | Mobile App | Stable, New Development, In Progress | Android: v1.7.2 → v1.7.3 iOS: V1.3.6 → V1.3.7 | IOS V1.3.6 (8 Jul 2026) ANDROID v1.7.2 (8 Jul 2026) | 26 | 26
3 | Punjab Flood Monitoring | Web | New Development | — → V1.0.0 | — | 41 | 42
4 | Purchase Module | Web | New Development, In Progress, Testing | 1.0.2 → 1.0.3 | — | 23 | 25
5 | SWSM | Web | Started, In Progress | V2.0.0 → V3.0.0 | — | 1 | 1
6 | General Project | Web | Started, Stable, In Progress | — → 0 | — | 3 | 3
7 | Savio | Web | Yet to Start, N/A | — → V1.0.0 | — | 1 | 1
8 | GMDA - JAL Mitra | Mobile App | — | Android: — → V1.0.0 iOS: — → V1.0.0 | — | 1 | 2
9 | NLC Dashboard (Network light control system) | Web | Testing, In Progress, Automation | — → V1.0.0 | — | 12 | 14
10 | Engineering Document | Web | On Hold, In Progress | — → N/A | — | 0 | 0
11 | WebScanet - GMDA | Web | Completed | — → 3.4.7 | — | 1 | 1
12 | onboardify 2.0 | Web | On Hold, In Progress | N/A → v1.0.0 | — | 3 | 3
13 | Tender 360 | Web | New Development, Stable, Testing | V2.4.5 → V2.4.6 | WEB V2.4.5 (9 Jul 2026) WEB V2.4.4 (9 Jul 2026) | 26 | 28
14 | Parvati Application | Mobile App | Stable | Android: V1.0.0 → V1.0.1 iOS: V1.0.0 → V1.0.1 | — | 4 | 4
15 | Tender Submission Automation | Web | Testing, In Progress | V2.2.4 → V2.5.4 | WEB V2.5.3 (23 Jun 2026) WEB V2.2.4 (17 Jun 2026) | 8 | 8
16 | CMS - Urban Voice | Web | Stable, Completed, Blocker | V1.0.0 → v2.0.0 | — | 15 | 15

## Tasks
# | Task Name | Project(s) | Status | Priority | Developer(s) | Start Date | End Date | Completed Date | Tags | Description
1 | Vendor - Full lifecycle automation using playwright | Purchase Module | Done | Medium | Khush Mevada | 2026-08-27 | 2026-08-27 | 2026-08-27 06:30 |  | include all the existing test cases and create one consolidated spec test cases which includes all.
2 | Vendor - PO Generation dropdown validation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-27 | 2026-08-27 | 2026-08-27 06:30
3 | Vendor database approval & rejection flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-26 | 2026-08-26 | 2026-08-26 06:30
4 | Vendor Database module automation set up | Purchase Module | Done | Medium | Khush Mevada | 2026-08-26 | 2026-08-26 | 2026-08-26 06:30 |  | get all the locators, and set up the flow
5 | Account approval - Vendor flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-26 | 2026-08-26 | 2026-08-26 06:30
6 | Search Edge-cases automation in vendor | Purchase Module | Done | Medium | Khush Mevada | 2026-08-25 | 2026-08-25 | 2026-08-25 06:30
7 | Vendor automation for file validation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-25 | 2026-08-25 | 2026-08-25 06:30
8 | Account team Vendor approval flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-25 | 2026-08-27 | 2026-08-26 06:30 |  | implement the automation for the vendor approval from the account team.
9 | Vendor testcase sheet | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-25 | 2026-08-25 06:30 |  | create a test case excel sheet for the vendor module of purchase module
10 | Full vendor workflow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-24 | 2026-08-24 06:30
11 | Edit vendor automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-24 | 2026-08-24 06:30
12 | Vendor registration validation automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-24 | 2026-08-24 06:30
13 | Vendor Conditional approval flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-24 | 2026-08-24 06:30
14 | Vendor Validation automation flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-21 | 2026-08-21 | 2026-08-21 06:30
15 | Vendor Rejection flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-21 | 2026-08-21 06:30
16 | Vendor view data validation automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-21 | 2026-08-21 06:30
17 | Vendor approval flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-21 | 2026-08-21 06:30
18 | Vendor Registration flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-20 | 2026-08-20 06:30
19 | Login test suit for the different roles | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-20 | 2026-08-20 06:30
20 | Locator extractions | Purchase Module | Done | Medium | — | 2026-08-19 | 2026-08-20 | 2026-08-20 06:30 |  | Extract the locators from the purchase module login and dashboard
21 | Close RFQA Tickets for punjab project | Punjab Flood Monitoring | In Progress | Medium | Harihar Upadhyay, Rutvik Panchal | 2026-08-19 | 2026-08-20
22 | Prepare a test planning for modules | Purchase Module | Done | Medium | Khush Mevada | 2026-08-18 | 2026-08-25 | 2026-08-24 06:30 |  | prepare the test planning for the purchase module sub modules
23 | Prepare understanding flow document for purchase module | Purchase Module | Done | Medium | Khush Mevada | 2026-08-18 | 2026-08-19 | 2026-08-19 06:30
24 | Purchase module KT | Purchase Module | Done | Medium | Khush Mevada | 2026-08-18 | 2026-08-18 | 2026-08-18 06:30
25 | CIMTrack - plot google maps | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-18 | 2026-08-18 | 2026-08-18 06:30 |  | plot the google map for the Dhruv krishna's distances for 03-04-26, 20-06-2026, 14-05-26, 20-05-26
26 | Document go through | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 |  | go through the mail sanket shared and do a brainstorming for the new functionality
27 | Punjab flood - ML logic document updation | Punjab Flood Monitoring | Done | Medium | Viraj Soni | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 |  | do a discussion with viraj and verify that do we actually take the travel distance and travel time given in the line diagram to train the ML modal
28 | Close Application RFQA tickets | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 |  | - https://cimcondigital.atlassian.net/browse/P4PFM-155 - Close the RFQA ticket.
29 | Punjab flood - Sanity Test | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 |  | Do a sanity test in the QA instance
30 | Punjab flood - Data flow validation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 |  | Validate the data indexing performed by harihar based on shared line diagram
31 | Punjab flood - KT session for edit functionality | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-17 | 2026-08-18 | 2026-08-18 06:30
32 | Document go-through | Punjab Flood Monitoring | Done | Medium | Viraj Soni | 2026-08-13 | 2026-08-13 | 2026-08-13 06:30 |  | Go through the documents of prediction modal with viraj and get as much info as possible.
33 | Close new RFQA tickets - punjab flood | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-13 | 2026-08-13 | 2026-08-13 06:30
34 | New Requirement Ticket generation for Punjab project | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal | 2026-08-14 | 2026-08-14 | 2026-08-14 06:30
35 | CIMTrack - document go through | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-12 | 2026-08-12 | 2026-08-12 06:30 |  | go through the document given by Sanket for the new requirement
36 | Punjab Flod\od - new requirement ticket creation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-12 | 2026-08-12 | 2026-08-12 06:30
37 | Punjab Flood monitoring - Backlog ticket closing | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Yash Padariya, Nilesh Bhil | 2026-08-11 | 2026-08-11 | 2026-08-11 06:30
38 | CIMtrack - Confluence Release note | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-11 | 2026-08-11 | 2026-08-11 06:30 |  | Create a confluence release note from the JIRA releases.
39 | CIMTrack - Release mail | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-11 | 2026-08-11 | 2026-08-11 06:30 |  | Draft and sent the release mail to the higher management.
40 | Punjab - new requirement ticket creation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-11 | 2026-08-11 | 2026-08-11 06:30 |  | 1. Device Name : Device name(e.g., AWLR 2047) should be shown below the site name (in small font size) 2. Dashboard Tiles (Tabs) : The following dashboard tiles should have the option to be shown or hidden as required: 3. In tile “Site status” detail page of high/medium/ low/normal site is not opening. 4. Manual Reading : In the Manual Reading Entry section, the Water Level field should support both Feet and Meter units for entering water-level readings. An Edit button should be provided for both Manual Readings and Sensor Readings, allowing authorized users to modify the recorded readings. 5. Reports & Analytics Module Access : If the Reports & Analytics module is disabled for a user from the Admin ID, the “Details” button should be removed from that user’s Sites table on the Dashboard. This is required because the Details page currently provides access to Reports and Export functionality. 6. Manual Alert Placement : Move the Manual Alert/SOS functionality from the Site Details page to the Dashboard.
41 | SWSM KT | SWSM | Done | Medium | Sanket Bhimani | 2026-08-10 | 2026-08-10 | 2026-08-10 06:30 |  | KT Session with Sanket
42 | CIMTrack dashboard release | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-10 | 2026-08-10 | 2026-08-10 06:30 |  | - Release note creation - Release mail - JIRA Release ticket management - Confluence management
43 | Punjab - RFQA ticket closing | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-10 | 2026-08-10 | 2026-08-10 06:30 |  | close all the remaining tickets from the JIRA
44 | Deployment | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-10 | 2026-08-10 | 2026-08-10 06:30 |  | Monitor the deployment of new requirements of the Punjab client.
45 | Ticket Creation - Punjab Flood project | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Yash Padariya, Nilesh Bhil | 2026-08-07 | 2026-08-07 | 2026-08-07 06:30 |  | create ticket of the client feedback and requirements.
46 | Resolve client queries and doubts | Punjab Flood Monitoring | Done | Medium | — | 2026-08-06 | 2026-08-06 | 2026-08-06 06:30 |  | Rajnish sir shared the message to Sandip sir with points that enhancements are not done and there are issues in it.
47 | Punjab - VPN & server configuration | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-05 | 2026-08-05 | 2026-08-05 06:30
48 | Punjab flood monitoring - new requirement validation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-05 | 2026-08-05 | 2026-08-06 06:30 |  | Verify Mobile application changes and dashboard changes.
49 | CIMTrack - RFQA ticket closing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-05 | 2026-08-06 | 2026-08-06 06:30 |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-657 https://cimcondigital.atlassian.net/browse/CIMTRACK-677 https://cimcondigital.atlassian.net/browse/CIMTRACK-719 https://cimcondigital.atlassian.net/browse/CIMTRACK-720 https://cimcondigital.atlassian.net/browse/CIMTRACK-721 https://cimcondigital.atlassian.net/browse/CIMTRACK-722 https://cimcondigital.atlassian.net/browse/CIMTRACK-723 https://cimcondigital.atlassian.net/browse/CIMTRACK-724 https://cimcondigital.atlassian.net/browse/CIMTRACK-728 https://cimcondigital.atlassian.net/browse/CIMTRACK-745
50 | NLC - Device configuration and command visibility | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-08-04 | 2026-08-04 | 2026-08-04 06:30
51 | Requirement go through | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Yash Padariya, Nilesh Bhil | 2026-08-04 | 2026-08-04 | 2026-08-04 06:30 |  | go through the requirements shared by the client.
52 | Punjab flood monitoring - service understanding | Punjab Flood Monitoring | Done | Medium | Nilesh Bhil | 2026-08-03 | 2026-08-03 | 2026-08-03 06:30 |  | Discuss & understand the working services in the Punjab flood project for notification and alert escalation
53 | Punjab Flood - Task RFQA tickets | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-03 | 2026-08-03 | 2026-08-03 06:30 |  | https://cimcondigital.atlassian.net/browse/P4PFM-93 https://cimcondigital.atlassian.net/browse/P4PFM-101 https://cimcondigital.atlassian.net/browse/P4PFM-106 https://cimcondigital.atlassian.net/browse/P4PFM-102 https://cimcondigital.atlassian.net/browse/P4PFM-103 https://cimcondigital.atlassian.net/browse/P4PFM-110 https://cimcondigital.atlassian.net/browse/P4PFM-61 https://cimcondigital.atlassian.net/browse/P4PFM-27 https://cimcondigital.atlassian.net/browse/P4PFM-63 https://cimcondigital.atlassian.net/browse/P4PFM-104
54 | CIMTrack - new sprint creation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-03 | 2026-08-03 | 2026-08-03 06:30 |  | create a new sprint for the backend release of DAR module.
55 | Ticket creation for identified points | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-01 | 2026-08-03 | 2026-08-03 06:30
56 | Punjab Flood Monitoring – Demo Release Testing and Validation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-01 | 2026-08-01 | 2026-08-03 06:30 |  | Perform testing and validation activities for the client demo release to ensure application stability and verify that existing functionalities work as expected across different environments.
57 | Punjab Flood Monitoring – Universal User Role-Based Login Validation Automation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-01 | 2026-08-01 | 2026-08-01 06:30 |  | Develop a universal automation script to validate role-based user login for all existing and future user designations. The script should dynamically adapt to updated roles without relying on hardcoded values or additional maintenance.
58 | Tender Ai manual verification after test cases | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-08-01 | 2026-08-01 | 2026-08-01 06:30
59 | Tender AI - Test Cases | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-08-01 | 2026-08-01 | 2026-08-01 06:30
60 | Default user password ticket closing | Punjab Flood Monitoring | Done | Medium | Nilesh Bhil | 2026-07-31 | 2026-08-01 | 2026-08-03 06:30 |  | https://cimcondigital.atlassian.net/browse/P4PFM-99
61 | Punjab new RFQA ticket closing | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-31 | 2026-08-03 | 2026-08-03 06:30 |  | https://cimcondigital.atlassian.net/browse/P4PFM-78 https://cimcondigital.atlassian.net/browse/P4PFM-93 https://cimcondigital.atlassian.net/browse/P4PFM-102 https://cimcondigital.atlassian.net/browse/P4PFM-103 https://cimcondigital.atlassian.net/browse/P4PFM-106
62 | Meeting with Sandip sir for Punjab project | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Yash Padariya, Nilesh Bhil | 2026-07-31 | 2026-07-31 | 2026-07-31 06:30
63 | CIMTrack DAR module ticket closing & test case updation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 |  | close https://cimcondigital.atlassian.net/browse/CIMTRACK-694 ticket and update the test case sheet as well and attach in the ticket.
64 | Punjab - Close all RFQA tickets - Nilesh bhill | Punjab Flood Monitoring | Done | Medium | Nilesh Bhil | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 |  | https://cimcondigital.atlassian.net/browse/P4PFM-75 https://cimcondigital.atlassian.net/browse/P4PFM-77 https://cimcondigital.atlassian.net/browse/P4PFM-83 https://cimcondigital.atlassian.net/browse/P4PFM-84 https://cimcondigital.atlassian.net/browse/P4PFM-86 https://cimcondigital.atlassian.net/browse/P4PFM-89 https://cimcondigital.atlassian.net/browse/P4PFM-96
65 | forgot password otp ticket. | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 |  | Create ticket for the correct message display in the modal.
66 | Punjab - Close all RFQA tickets - Harihar | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 |  | Close : https://cimcondigital.atlassian.net/browse/P4PFM-79 https://cimcondigital.atlassian.net/browse/P4PFM-80 https://cimcondigital.atlassian.net/browse/P4PFM-82 https://cimcondigital.atlassian.net/browse/P4PFM-94 https://cimcondigital.atlassian.net/browse/P4PFM-95 https://cimcondigital.atlassian.net/browse/P4PFM-97
67 | CIMTrack - DAR RFQA Ticket closing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-740 https://cimcondigital.atlassian.net/browse/CIMTRACK-741 https://cimcondigital.atlassian.net/browse/CIMTRACK-742 https://cimcondigital.atlassian.net/browse/CIMTRACK-743 https://cimcondigital.atlassian.net/browse/CIMTRACK-744 Close this tickets.
68 | Create Punjab tickets | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-30 | 2026-07-30 | 2026-07-30 06:30 |  | create tickets for the discussed points with harihar
69 | Role-Based Credential Verification | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Nilesh Bhil | 2026-07-30 | 2026-07-30 | 2026-07-30 06:30 |  | Verify that all user credentials are working correctly according to their assigned roles and permissions. Check access for each role and identify any permission or login issues.
70 | Discussion with harihar | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-30 | 2026-07-30 | 2026-07-30 06:30 |  | Discussion with harihar regarding the issues
71 | CIMTrack ticket creation for DAR module | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-27 | 2026-07-30 | 2026-07-30 06:30 |  | create the DAR module ticket for the 5 points which were discovered during the testing
72 | Create Jira for the NLC issue of data loading hang | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-27 | 2026-07-30 | 2026-07-30 06:30
73 | GMDA - Jal Mitra KT | GMDA - JAL Mitra | Done | Medium | Rutvik Panchal | 2026-07-06 | 2026-07-16 | 2026-07-28 06:30
74 | CIMTrack - DAR Module dashboard testing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-28 | 2026-07-28 | 2026-07-28 06:30
75 | NLC - Device connectivity issue root cause analysis | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-27 | 2026-07-27 | 2026-07-27 06:30
76 | CIMTrack - Mobile UI Designing v2 | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-27 | 2026-07-28 | 2026-07-28 06:30 |  | Attendance Page, History page and User page.
77 | NLC - new 250 Device validation | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-24 | 2026-07-27 | 2026-07-27 06:30 | System issue | new devices are not able to send the data to thingsboard
78 | Punjab flood iOS testing | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-07-27 | 2026-07-27 | 2026-07-27 06:30
79 | CIMTrack - DAR module dashboard testcase creation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-27 | 2026-07-27 | 2026-07-27 06:30
80 | New 250 NLC Device configuration | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-24 | 2026-07-24 | 2026-07-24 06:30
81 | CIMTrack - Mobile UI Designing | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-24 | 2026-07-24 | 2026-07-24 06:30 |  | Splash screen, Login page & Home page
82 | Weekly update to sandip sir | General Project | Done | Medium | — | 2026-07-22 | 2026-07-22 | 2026-07-22 06:30
83 | User Guide screenshot uploading | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Yash Padariya, Nilesh Bhil | 2026-07-22 | 2026-08-07 | 2026-08-03 06:30
84 | CIMTrack UI Redesign meeting | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-21 | 2026-07-21 | 2026-07-21 06:30 |  | conduct a meeting with farman and team for the new ui review and discussion
85 | PFM - RFQA ticket closing | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-07-20 | 2026-07-21 | 2026-07-21 06:30 |  | https://cimcondigital.atlassian.net/browse/P4PFM-73 https://cimcondigital.atlassian.net/browse/P4PFM-74 https://cimcondigital.atlassian.net/browse/P4PFM-85 https://cimcondigital.atlassian.net/browse/P4PFM-87 https://cimcondigital.atlassian.net/browse/P4PFM-88 https://cimcondigital.atlassian.net/browse/P4PFM-90
86 | PFM - Web Dashboard testing | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-07-20 | 2026-07-25 | 2026-07-27 06:30 |  | i have stopped the testing as UT wasn't done by developer
87 | PFM - Mobile application testing | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-07-20 | 2026-07-21 | 2026-07-20 06:30
88 | CIMTrack Ticket closing | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-20 | 2026-08-01 | 2026-08-03 06:30 |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-698 https://cimcondigital.atlassian.net/browse/CIMTRACK-718
89 | Savio - ticket creation | Savio | Done | Medium | Dev Patel | 2026-07-18 | 2026-07-18 | 2026-07-18 06:30 |  | create ticket for all the points given by dev for improvements and bugs
90 | Punjab flood mobile test cases creation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-18 | 2026-07-21 | 2026-07-20 06:30 |  | It will take upto 5-6 hours
91 | Punjab Flood - Dashboard KT | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-18 | 2026-07-18 | 2026-07-18 06:30
92 | Punjab Flood - Mobile KT | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-07-17 | 2026-07-17 | 2026-07-17 06:30
93 | NLC - Multi Device upload | NLC Dashboard (Network light control system) | Done | High | Jil Shah | 2026-07-16 | 2026-07-16 | 2026-07-16 06:30
94 | NLC - Multi Devices configuration | NLC Dashboard (Network light control system) | Done | High | Jil Shah | 2026-07-16 | 2026-07-17 | 2026-07-17 06:30 |  | create a playwright script to configure the credentials in thingsboard NLC
95 | NLC -Monitoring Dashboard creation | NLC Dashboard (Network light control system) | Done | High | Jil Shah | 2026-07-15 | 2026-07-18 | 2026-07-17 06:30
96 | AI360 discussion | General Project | Done | Low | — | 2026-07-15 | 2026-07-15 | 2026-07-15 06:30 |  | Discussion with sandip sir and AI-ML team.
97 | NLC - Load testing script creation | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-15 | 2026-07-20 | 2026-07-15 06:30
98 | NLC - Load testing planning | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-14 | 2026-07-14 | 2026-07-14 06:30
99 | CIMTrack Redesign meeting | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-13 | 2026-07-13 | 2026-07-13 06:30
100 | Create JIRA Tickets | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-10 | 2026-07-10 | 2026-07-10 06:30 |  | Jira tickets for the points suggested by Lokesh ji and Jutan sir.
101 | CIMTrack sprint 4 planning | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-09 | 2026-07-09 | 2026-07-09 06:30
102 | CIMTrack Ticket creation | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-09 | 2026-07-09 | 2026-07-09 06:30 |  | Create tickets for the remaining points of sprint 4
103 | T360 Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-07-08 | 2026-07-10 | 2026-07-09 06:30 |  | https://cimcondigital.atlassian.net/browse/T3-118 https://cimcondigital.atlassian.net/browse/T3-137 https://cimcondigital.atlassian.net/browse/T3-138 https://cimcondigital.atlassian.net/browse/T3-128 https://cimcondigital.atlassian.net/browse/T3-140 https://cimcondigital.atlassian.net/browse/T3-141 https://cimcondigital.atlassian.net/browse/T3-142 https://cimcondigital.atlassian.net/browse/T3-143 https://cimcondigital.atlassian.net/browse/T3-139
104 | TSA Meeting | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-07-08 | 2026-07-08 | 2026-07-08 06:30
105 | CIMTrack Dashboard V1.5 Release Note JIRA | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-07 | 2026-07-07 | 2026-07-07 06:30
106 | CIMTrack Dashboard V1.5.0 Release | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-07 | 2026-07-07 | 2026-07-07 06:30
107 | Onboardify - User Guide Creation | onboardify 2.0 | Done | Medium | Shreya Vashishtha | 2026-07-06 | 2026-07-11 | 2026-07-08 06:30
108 | Tender360 - Feedback ticket generation | Tender 360 | Done | Medium | Dev Patel | 2026-07-06 | 2026-07-07 | 2026-07-07 06:30
109 | Create Jira Ticket | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-06 | 2026-07-06 | 2026-07-06 06:30 |  | The following changes have been implemented: 1. In Voucher Approval, under the Conveyance - 2 Wheeler and Conveyance - 4 Wheeler voucher sections, the CIMTrack Calculated KM and Route columns have been removed. Only the Claim KM column is now displayed. 2. The Expense Head-wise Grouping feature has been implemented and is now available within the Expense Head Summary accordion. 3. A filter has also been added to the Expense Head column in the Line Items section to make it easier to filter and review expense records.
110 | CIMTrack Release Ticket closing | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-04 | 2026-07-04 | 2026-07-04 06:30
111 | Sales Automation overview | General Project | Done | Medium | — | 2026-07-03 |  | 2026-08-18 06:30
112 | refactor CIMTrack JIRA Completely | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-04 | 2026-07-03 06:30
113 | Tender360 Release note preparation | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30
114 | Tender360 Release points preparation | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30
115 | CIMTrack Release note & mail preparation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30
116 | Tender360 - Close the remaining topic | Tender 360 | Done | Medium | Dev Patel | 2026-07-02 | 2026-07-02 | 2026-07-02 06:30
117 | GMDA - Jal Mitra Test Cases creation | GMDA - JAL Mitra | To-Do | Low | Rutvik Panchal | 2026-07-06 | 2026-07-24
118 | Create ticket for the file upload Mandatory for the daily activity report. | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-02 | 2026-07-02 | 2026-07-02 06:30
119 | CIMTrack PM Dashboard Release note creation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-02 | 2026-07-04 | 2026-07-03 06:30
120 | CIMTrack - PM Dashboard Testing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-01 | 2026-07-01 | 2026-07-01 06:30
121 | CMS - bifurcate the test types file strcuture. | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-30 | 2026-06-30 | 2026-06-30 06:30
122 | CMS - Smoke Testing bifurcation in automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-29 | 2026-06-29 | 2026-06-29 06:30
123 | NLC KT | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-06-27 | 2026-06-27 | 2026-06-27 06:30
124 | Tender360 - Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-30 |  | 2026-07-02 06:30 |  | https://cimcondigital.atlassian.net/browse/T3-124 https://cimcondigital.atlassian.net/browse/T3-127 https://cimcondigital.atlassian.net/browse/T3-132 https://cimcondigital.atlassian.net/browse/T3-134
125 | CMS - User Management Filter Automation & Validation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-29 | 2026-06-26 06:30
126 | CMS - Impersonate user Automation flow & Validation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-29 | 2026-06-26 06:30
127 | CMS - Edit User Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30
128 | CMS - User Deactivation Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30
129 | Tender360 - Ticket creation | Tender 360 | Done | Medium | Dev Patel | 2026-06-25 | 2026-06-26 | 2026-06-26 06:30 |  | Create the tickets after the meeting with Komal ma'am and sandip sir.
130 | CMS - User Set up Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-29 06:30
131 | CMS - User Activation Flow automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30
132 | NLC - KT | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-06-25 | 2026-06-25 | 2026-06-25 06:30
133 | CMS - Load testing setup | CMS - Urban Voice | Done | Medium | — | 2026-06-11 | 2026-06-12 | 2026-06-12 06:30
134 | Onboardify KT & Project Discussion | onboardify 2.0 | Done | Low | — | 2026-06-24 | 2026-06-24 | 2026-06-25 05:04
135 | UrbanVoice - Home page | CMS - Urban Voice | Done | Low | Harihar Upadhyay | 2026-06-24 | 2026-06-26 | 2026-06-26 06:30 |  | Enhance the front-end
136 | Tender360 v2.4.3 KT Meeting | Tender 360 | Done | Medium | Dev Patel | 2026-06-24 | 2026-06-24
137 | Tender360 - 4 Hours Threshold Ticket Creationg | Tender 360 | Done | Medium | Dev Patel | 2026-06-24 | 2026-06-24
138 | Punjab Flood Monitoring Meeting MOM | Punjab Flood Monitoring | Done | Medium | — | 2026-06-23 | 2026-06-23
139 | Tender360 V2.4.3 Release | Tender 360 | Done | Medium | Dev Patel | 2026-06-23 | 2026-06-23
140 | Tender360 - Script Enhancement | Tender 360 | Done | Medium | Dev Patel | 2026-06-23 |  | 2026-07-13 06:30
141 | Tender360 Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-22 | 2026-06-23 |  |  | https://cimcondigital.atlassian.net/browse/T3-113 https://cimcondigital.atlassian.net/browse/T3-116 https://cimcondigital.atlassian.net/browse/T3-104 https://cimcondigital.atlassian.net/browse/T3-114 https://cimcondigital.atlassian.net/browse/T3-115 https://cimcondigital.atlassian.net/browse/T3-108
142 | Tender Automation - Ticket Creation | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-22 | 2026-06-22 |  |  | 1. Tender Documents – I have re-uploaded the tender documents. The financial document selection is now correct as per my last observation. However, there is still an issue with the fillable forms — the tool is currently preparing a single form for multiple tender forms. This needs to be resolved at the earliest. 2. Next Upgrade – Experience Document Selection Moving forward, the next enhancement involves the selection of experience documents within the tool. As discussed with both of you, kindly incorporate a toggle-type bar for the following sectors: - Water - Oil & Gas (O&G) - Lighting 3. Document Source – OneDrive Integration The selection of documents should be fetched directly from OneDrive (not from a local server), so that we can use and prepare the documents remotely as needed.
143 | CIMTrack Travel Script Test after production release | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-06-22 | 2026-06-23 |  |  | Please check satya Prakash baghel and kapil dev nigam last 2 days comparison needed for actual travel and our script calculated travel
144 | CMS - Ticket Closing | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-19 | 2026-06-20
145 | TSA - Final Bid grouping testing | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-19 | 2026-06-25 | 2026-06-25 06:30 |  | https://cimcondigital.atlassian.net/browse/TSA-39
146 | Tender360 - Ticket closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-19 | 2026-06-19 |  |  | https://cimcondigital.atlassian.net/browse/T3-110 https://cimcondigital.atlassian.net/browse/T3-104 https://cimcondigital.atlassian.net/browse/T3-115 https://cimcondigital.atlassian.net/browse/T3-100 https://cimcondigital.atlassian.net/browse/T3-111 https://cimcondigital.atlassian.net/browse/T3-112 https://cimcondigital.atlassian.net/browse/T3-107
147 | Tender360 - Corrigendum Documents | Tender 360 | Done | Medium | Dev Patel | 2026-06-18 | 2026-06-18 |  |  | https://cimcondigital.atlassian.net/browse/T3-108
148 | CMS - User Management Automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-17 |  | 2026-06-25 06:30
149 | Tender360 - New ticket creation for the requirements. | Tender 360 | Done | High | Dev Patel | 2026-06-17 | 2026-06-17 |  |  | 1.AOC- winners list 2.prompt - admin control dynamic prompt(setting) 3.status - accept for bidding 4. notification
150 | Tender 360 - Ticket Closing | Tender 360 | Done | Urgent | Dev Patel | 2026-06-17 | 2026-06-17 |  |  | https://cimcondigital.atlassian.net/browse/T3-85 https://cimcondigital.atlassian.net/browse/T3-109 https://cimcondigital.atlassian.net/browse/T3-106 https://cimcondigital.atlassian.net/browse/T3-102 https://cimcondigital.atlassian.net/browse/T3-104
151 | CMS - Production Release | CMS - Urban Voice | Done | High | Harihar Upadhyay | 2026-06-12 |  | 2026-07-13 06:30
152 | Tender360 - Tender scrapping script initial enhancement | Tender 360 | Done | Medium | Dev Patel | 2026-06-12 | 2026-06-12
153 | CMS - Initial Login load testing set up | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-12 | 2026-07-13 | 2026-07-13 06:30
154 | CIMTrack - Geo Tag Testing | CIMTrack | Done | Medium | Rutvik Panchal | 2026-06-03 | 2026-06-04 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-687
155 | TSA - Tickets creation | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-10 | 2026-06-10 |  |  | create ticket for the tickets / points
156 | CIMTrack - give discussion points | CIMTrack | Done | Medium | Rutvik Panchal | 2026-06-10 | 2026-06-10
157 | Tender360 - Ticket creation | Tender 360 | Done | Medium | Dev Patel | 2026-06-10 | 2026-06-10 |  |  | Create all tickets discussed with the himanshu
158 | CIMTrack - Data Migration Validation | CIMTrack Dashboard | Done | Urgent | Sanket Bhimani | 2026-06-06 | 2026-06-06
159 | CMS 2.0 - Iteration 2 Testing | CMS - Urban Voice | Done | Urgent | Harihar Upadhyay | 2026-06-05 | 2026-06-10
160 | Tender360 - Discovered Tender page Testing | Tender 360 | Done | — | Dev Patel | 2026-06-05 | 2026-06-05
161 | Tender360 - Discovered Tender Page Test Case writting | Tender 360 | Done | — | Dev Patel | 2026-06-05 | 2026-06-05
162 | Onboardify - Positive Testing | Tender Submission Automation | Done | — | Viraj Soni | 2026-06-03 | 2026-06-06
163 | Tender 360 - OCR Testing | Tender 360 | Done | Medium | Dev Patel | 2026-06-02 | 2026-06-05 |  |  | https://cimcondigital.atlassian.net/browse/T3-76
164 | CIMTrack New Build Test | CIMTrack | Done | Low | Rutvik Panchal | 2026-05-30 | 2026-06-10 |  |  | 1. mime type change ( should be able to share on teams ) 2. New Message display for multiple try to check-in & check-out ( you have reached your limit message removed)
165 | CIMTrack - 672 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-29 | 2026-06-03 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-672
166 | GMDA Testing & Release | WebScanet - GMDA | Done | Medium | — | 2026-05-29 |  | 2026-08-11 06:30
167 | Parvati - iOS testing | Parvati Application | Done | — | Prakash Patel | 2026-05-28 | 2026-05-29
168 | CIMTrack - Distance Script Testing | CIMTrack Dashboard | Done | — | Sanket Bhimani | 2026-05-27 | 2026-06-09
169 | CIMTrack - 683 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-29 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-683
170 | CIMTrack - 682 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-29 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-682
171 | CIMTrack - 679 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-27 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-679?atlOrigin=eyJpIjoiMjc0YjExOGU1MThhNDliNWI1ZjEyMTk1NGRjYzM4ZWEiLCJwIjoiaiJ9
172 | CIMTrack 678 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-27 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-678?atlOrigin=eyJpIjoiNGE5NDRkY2ViZjliNDc0OWI4NDFkNjM5NWI4MjMyNWYiLCJwIjoiaiJ9
173 | Parvati iOS Testing | Parvati Application | Done | — | Prakash Patel | 2026-05-27 | 2026-05-29
174 | Onboadify KT | onboardify 2.0 | Done | — | Shreya Vashishtha | 2026-05-27 | 2026-05-27
175 | CIMTrack Force Password Change | CIMTrack | Done | — | Rutvik Panchal | 2026-05-25 | 2026-05-29
176 | CIMTrack Forgot Password Testing | CIMTrack | Done | — | — | 2026-05-25 | 2026-05-29
177 | CIMTrack Battery Consumption optimization test | CIMTrack | Done | — | — | 2026-05-25 | 2026-06-01 |  |  | Test this for a week with different scenario
178 | Tender360 - First Release - V1.0.0 | Tender 360 | Done | — | — | 2026-05-20 | 2026-05-20
179 | CIMTrack - KT | CIMTrack | Done | — | — | 2026-05-20 | 2026-05-20 |  |  | new Distance calculation script KT
180 | TSA all tickets in RFQA | Tender Submission Automation | Done | — | — | 2026-05-20 | 2026-05-29 |  |  | should be able to complete this week or next week.
181 | CIMTrack Ticket verification | CIMTrack | Done | — | — | 2026-05-25 | 2026-05-29
182 | Tender 360 Initial Testing | Tender 360 | Done | — | — | 2026-05-19 | 2026-05-20 |  |  | Test the core functionality and give first release to Marketing team
183 | Parvati KT | Parvati Application | Done | — | — | 2026-05-18 | 2026-05-18 |  |  | give the parvati KT to Gulab bhai
184 | Parvati Release | Parvati Application | Done | — | — | 2026-05-18 | 2026-05-18 |  |  | Revalidate the issue points and retest the application.
185 | User Guide for Expense Module | CIMTrack | Done | — | — | 2026-05-16 | 2026-05-22 |  | User Guide | Create the user guide for the Expense module same as Daily activity
186 | CIMTrack previous Jira Ticket Resolutions | CIMTrack Dashboard | Done | — | — | 2026-05-16 | 2026-05-23 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-594 https://cimcondigital.atlassian.net/browse/CIMTRACK-57 https://cimcondigital.atlassian.net/browse/CIMTRACK-82 https://cimcondigital.atlassian.net/browse/CIMTRACK-106 https://cimcondigital.atlassian.net/browse/CIMTRACK-109 https://cimcondigital.atlassian.net/browse/CIMTRACK-119 https://cimcondigital.atlassian.net/browse/CIMTRACK-121 https://cimcondigital.atlassian.net/browse/CIMTRACK-122 https://cimcondigital.atlassian.net/browse/CIMTRACK-124 https://cimcondigital.atlassian.net/browse/CIMTRACK-125 https://cimcondigital.atlassian.net/browse/CIMTRACK-127 https://cimcondigital.atlassian.net/browse/CIMTRACK-134 https://cimcondigital.atlassian.net/browse/CIMTRACK-141 https://cimcondigital.atlassian.net/browse/CIMTRACK-142 https://cimcondigital.atlassian.net/browse/CIMTRACK-347 https://cimcondigital.atlassian.net/browse/CIMTRACK-348 https://cimcondigital.atlassian.net/browse/CIMTRACK-350 https://cimcondigital.atlassian.net/browse/CIMTRACK-366 https://cimcondigital.atlassian.net/browse/CIMTRACK-370 https://cimcondigital.atlassian.net/browse/CIMTRACK-371 https://cimcondigital.atlassian.net/browse/CIMTRACK-372 https://cimcondigital.atlassian.net/browse/CIMTRACK-378 https://cimcondigital.atlassian.net/browse/CIMTRACK-379 https://cimcondigital.atlassian.net/browse/CIMTRACK-380 https://cimcondigital.atlassian.net/browse/CIMTRACK-397 https://cimcondigital.atlassian.net/browse/CIMTRACK-398 https://cimcondigital.atlassian.net/browse/CIMTRACK-402
187 | No data loss verification | Tender 360 | Done | — | Dev Patel | 2026-05-16 | 2026-05-16 |  | Validation, Manual Testing | once the project is on testing server, validate all 5 dashboards and confirm that there is no data loss.
188 | Tender 360 KT | Tender 360 | Done | — | Dev Patel | 2026-05-16 | 2026-05-18
189 | Test the Expense Voucher Flow | CIMTrack Dashboard | Done | — | — | 2026-05-15 | 2026-06-12 |  |  | Total 264 Test cases are done, now test it.

## Releases
Manual Releases — Total: 13
# | Release Name | Project(s) | Version(s) | Status | Release Date | Manager | Developers
1 | CIMTrack Sprint 4.1 | CIMTrack Dashboard | v1.6 | Released | 2026-08-11 | Dwip Pandya | Sanket Bhimani
2 | Tender360 - V2.4.5 | Tender 360 | V2.4.5 | Released | 2026-07-09 | Dwip Pandya | Dev Patel
3 | Tender360 - V2.4.4 | Tender 360 | V2.4.4 | Released | 2026-07-03 | Dwip Pandya | Dev Patel
4 | CIMTrack DAR Release | CIMTrack Dashboard | v1.5 | Released | 2026-07-07 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
5 | TSA V2.5.4 | Tender Submission Automation | V2.5.4 | Released | 2026-06-17 | Dwip Pandya | Viraj Soni
6 | Tender 360 Final Release | Tender 360 | V2.4.3 | Released | 2026-06-23 | Dwip Pandya | Dev Patel
7 | CIMTrack Sprint 3 - iOS | CIMTrack | V1.3.5 | Released | 2026-06-16 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
8 | CIMTrack Sprint 3 - Android | CIMTrack | v1.7.1 | Released | 2026-06-16 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
9 | Parvati Release | Parvati Application | V1.0.0 | Released | 2026-06-02 | Dwip Pandya | Prakash Patel
10 | T360 Release | Tender 360 | v1.0.0 | Released | 2026-05-22 | Dwip Pandya | Dev Patel
11 | TSA Initial Release | Tender Submission Automation | v1.0.0 | Released | 2026-04-27 | Dwip Pandya | Viraj Soni
12 | CIMTrack iOS Release | CIMTrack | V1.3.4 | Released | 2026-04-24 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
13 | CIMTrack Android Release | CIMTrack | V1.7.0 | Released | 2026-04-24 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
Release Points — Total: 7
# | Release Point Title | Project(s) | Type | Version(s) | Checklist Progress | Completed
1 | CIMTrack - Sprint 4.1 | CIMTrack Dashboard | Past | — | 18/18 | Yes
2 | T360 - V2.4.6 | Tender 360 | Past | V2.4.5 (Prev) | 11/11 | Yes
3 | CIMTrack - DAR Report | CIMTrack Dashboard, CIMTrack | Past | — | 11/11 | Yes
4 | Tender360 V2.4.4 | Tender 360 | Past | V2.4.4 (Up) | 11/11 | Yes
5 | TSA V2.2.4 Release | Tender Submission Automation | Past | V2.2.4 (Prev) | 10/10 | Yes
6 | Tender 360 Final Release | Tender 360 | Past | V2.4.3 (Prev) | 20/20 | Yes
7 | CIMTrack Sprint 3 | CIMTrack | Past | Android v1.7.1 (Prev), iOS V1.3.5 (Prev) | 15/15 | Yes

## Test Cases
Test Case Counts by Project
# | Project | Total Test Cases | Not executed | Passed | Failed | Blocked
1 | CIMTrack Dashboard | 765 | 0 | 724 | 41 | 0
2 | CIMTrack | 148 | 0 | 147 | 1 | 0
3 | Punjab Flood Monitoring | 125 | 0 | 123 | 1 | 1
4 | Purchase Module | 86 | 0 | 86 | 0 | 0
5 | SWSM | 0 | 0 | 0 | 0 | 0
6 | General Project | 0 | 0 | 0 | 0 | 0
7 | Savio | 0 | 0 | 0 | 0 | 0
8 | GMDA - JAL Mitra | 0 | 0 | 0 | 0 | 0
9 | NLC Dashboard (Network light control system) | 0 | 0 | 0 | 0 | 0
10 | Engineering Document | 0 | 0 | 0 | 0 | 0
11 | WebScanet - GMDA | 60 | 0 | 57 | 3 | 0
12 | onboardify 2.0 | 0 | 0 | 0 | 0 | 0
13 | Tender 360 | 60 | 0 | 60 | 0 | 0
14 | Parvati Application | 116 | 0 | 99 | 17 | 0
15 | Tender Submission Automation | 383 | 0 | 383 | 0 | 0
16 | CMS - Urban Voice | 277 | 0 | 248 | 28 | 1
| TOTAL | 2020 | 0 | 1927 | 91 | 2
By Priority
# | Priority | Count
1 | Critical | 0
2 | High | 1196
3 | Medium | 754
4 | Low | 70
By Type
# | Type | Count
1 | Manual | 1959
2 | Automated | 0
3 | API | 0
4 | Security | 44
5 | Performance | 12
6 | Regression | 5