## Overview
Clair — Project & Task Report
Generated 15/7/2026, 12:58:11 pm
15 | 96 | 12 | 6 | 1012
Projects | Tasks | Releases | Release Points | Test Cases
Applied Filters
Projects | All Projects
Developers | All Developers
Date Range | All Time
Task Status | All Statuses
Release Status | All Statuses
Test Case Status | All Statuses
Category Breakdown
Projects |  |  |  | 15
Tasks (in scope) |  |  |  | 96
Releases |  |  |  | 12
Release Points |  |  |  | 6
Test Cases |  |  |  | 1012

## Projects
# | Project Name | Type | Current Status | Version (Prev → Upcoming) | Past Released Versions | Completed Tasks | Total Tasks
1 | Savio | Web | Yet to Start, N/A | — → V1.0.0 | — | 0 | 0
2 | GMDA - JAL Mitra | Mobile App | — | Android: — → V1.0.0 iOS: — → V1.0.0 | — | 0 | 1
3 | NLC Dashboard (Network light control system) | Web | Testing, In Progress, Automation | — → V1.0.0 | — | 3 | 5
4 | Engineering Document | Web | On Hold, In Progress | — → N/A | — | 0 | 0
5 | Punjab Flood Monitoring | Web | New Development | — → V1.0.0 | — | 1 | 1
6 | GMDA Parvati - Application | Mobile App | Yet to Start, On Hold | Android: N/A → V1.0.0 iOS: N/A → V1.0.0 | — | 0 | 0
7 | WebScanet - GMDA | Web | Completed | — → 3.4.7 | — | 0 | 1
8 | onboardify 2.0 | Web | On Hold, In Progress | N/A → v1.0.0 | — | 3 | 3
9 | Purchase Module | Web | Yet to Start, New Development, In Progress | 1.0.2 → 1.0.3 | — | 0 | 0
10 | Tender 360 | Web | New Development, Stable, Testing | V2.4.5 → V2.4.6 | WEB V2.4.5 (9 Jul 2026) WEB V2.4.4 (9 Jul 2026) | 26 | 26
11 | Parvati Application | Mobile App | Stable | Android: V1.0.0 → V1.0.1 iOS: V1.0.0 → V1.0.1 | — | 4 | 4
12 | Tender Submission Automation | Web | Testing, In Progress | V2.2.4 → V2.5.4 | WEB V2.5.3 (23 Jun 2026) WEB V2.2.4 (17 Jun 2026) | 6 | 6
13 | CMS - Urban Voice | Web | Issue Assigned, In Progress, Testing | V1.0.0 → v2.0.0 | — | 15 | 15
14 | CIMTrack Dashboard | Web | Testing, Issue Assigned, New Development | v1.5 → v1.5.1 | — | 15 | 16
15 | CIMTrack | Mobile App | Stable, New Development, In Progress | Android: v1.7.2 → v1.7.3 iOS: V1.3.6 → V1.3.7 | IOS V1.3.6 (8 Jul 2026) ANDROID v1.7.2 (8 Jul 2026) | 21 | 21

## Tasks
# | Task Name | Project(s) | Status | Priority | Developer(s) | Start Date | End Date | Completed Date | Tags | Description
1 | NLC - Load testing script creation | NLC Dashboard (Network light control system) | In Progress | Medium | Jil Shah | 2026-07-15 | 2026-07-20
2 | NLC - Load testing planning | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-14 | 2026-07-14 | 2026-07-14 06:30
3 | CIMTrack Redesign meeting | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-13 | 2026-07-13 | 2026-07-13 06:30
4 | Create JIRA Tickets | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-10 | 2026-07-10 | 2026-07-10 06:30 |  | Jira tickets for the points suggested by Lokesh ji and Jutan sir.
5 | CIMTrack sprint 4 planning | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-09 | 2026-07-09 | 2026-07-09 06:30
6 | CIMTrack Ticket creation | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-09 | 2026-07-09 | 2026-07-09 06:30 |  | Create tickets for the remaining points of sprint 4
7 | T360 Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-07-08 | 2026-07-10 | 2026-07-09 06:30 |  | https://cimcondigital.atlassian.net/browse/T3-118 https://cimcondigital.atlassian.net/browse/T3-137 https://cimcondigital.atlassian.net/browse/T3-138 https://cimcondigital.atlassian.net/browse/T3-128 https://cimcondigital.atlassian.net/browse/T3-140 https://cimcondigital.atlassian.net/browse/T3-141 https://cimcondigital.atlassian.net/browse/T3-142 https://cimcondigital.atlassian.net/browse/T3-143 https://cimcondigital.atlassian.net/browse/T3-139
8 | TSA Meeting | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-07-08 | 2026-07-08 | 2026-07-08 06:30
9 | CIMTrack Dashboard V1.5 Release Note JIRA | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-07 | 2026-07-07 | 2026-07-07 06:30
10 | CIMTrack Dashboard V1.5.0 Release | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-07 | 2026-07-07 | 2026-07-07 06:30
11 | Onboardify - User Guide Creation | onboardify 2.0 | Done | Medium | Shreya Vashishtha | 2026-07-06 | 2026-07-11 | 2026-07-08 06:30
12 | Tender360 - Feedback ticket generation | Tender 360 | Done | Medium | Dev Patel | 2026-07-06 | 2026-07-07 | 2026-07-07 06:30
13 | Create Jira Ticket | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-06 | 2026-07-06 | 2026-07-06 06:30 |  | The following changes have been implemented: 1. In Voucher Approval, under the Conveyance - 2 Wheeler and Conveyance - 4 Wheeler voucher sections, the CIMTrack Calculated KM and Route columns have been removed. Only the Claim KM column is now displayed. 2. The Expense Head-wise Grouping feature has been implemented and is now available within the Expense Head Summary accordion. 3. A filter has also been added to the Expense Head column in the Line Items section to make it easier to filter and review expense records.
14 | CIMTrack Release Ticket closing | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-04 | 2026-07-04 | 2026-07-04 06:30
15 | refactor CIMTrack JIRA Completely | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-04 | 2026-07-03 06:30
16 | Tender360 Release note preparation | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30
17 | Tender360 Release points preparation | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30
18 | CIMTrack Release note & mail preparation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30
19 | Tender360 - Close the remaining topic | Tender 360 | Done | Medium | Dev Patel | 2026-07-02 | 2026-07-02 | 2026-07-02 06:30
20 | GMDA - Jal Mitra Test Cases creation | GMDA - JAL Mitra | To-Do | Medium | Rutvik Panchal | 2026-07-06 | 2026-07-17
21 | Create ticket for the file upload Mandatory for the daily activity report. | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-02 | 2026-07-02 | 2026-07-02 06:30
22 | CIMTrack PM Dashboard Release note creation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-02 | 2026-07-04 | 2026-07-03 06:30
23 | CIMTrack - PM Dashboard Testing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-01 | 2026-07-01 | 2026-07-01 06:30
24 | NLC - Manual Testing and Data validation | NLC Dashboard (Network light control system) | On Hold | Urgent | Jil Shah | 2026-07-01
25 | CMS - bifurcate the test types file strcuture. | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-30 | 2026-06-30 | 2026-06-30 06:30
26 | CMS - Smoke Testing bifurcation in automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-29 | 2026-06-29 | 2026-06-29 06:30
27 | NLC KT | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-06-27 | 2026-06-27 | 2026-06-27 06:30
28 | Tender360 - Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-30 |  | 2026-07-02 06:30 |  | https://cimcondigital.atlassian.net/browse/T3-124 https://cimcondigital.atlassian.net/browse/T3-127 https://cimcondigital.atlassian.net/browse/T3-132 https://cimcondigital.atlassian.net/browse/T3-134
29 | CMS - User Management Filter Automation & Validation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-29 | 2026-06-26 06:30
30 | CMS - Impersonate user Automation flow & Validation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-29 | 2026-06-26 06:30
31 | CMS - Edit User Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30
32 | CMS - User Deactivation Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30
33 | Tender360 - Ticket creation | Tender 360 | Done | Medium | Dev Patel | 2026-06-25 | 2026-06-26 | 2026-06-26 06:30 |  | Create the tickets after the meeting with Komal ma'am and sandip sir.
34 | CMS - User Set up Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-29 06:30
35 | CMS - User Activation Flow automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30
36 | NLC - KT | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-06-25 | 2026-06-25 | 2026-06-25 06:30
37 | CMS - Load testing setup | CMS - Urban Voice | Done | Medium | — | 2026-06-11 | 2026-06-12 | 2026-06-12 06:30
38 | Onboardify KT & Project Discussion | onboardify 2.0 | Done | Low | — | 2026-06-24 | 2026-06-24 | 2026-06-25 05:04
39 | UrbanVoice - Home page | CMS - Urban Voice | Done | Low | Harihar Upadhyay | 2026-06-24 | 2026-06-26 | 2026-06-26 06:30 |  | Enhance the front-end
40 | Tender360 v2.4.3 KT Meeting | Tender 360 | Done | Medium | Dev Patel | 2026-06-24 | 2026-06-24
41 | Tender360 - 4 Hours Threshold Ticket Creationg | Tender 360 | Done | Medium | Dev Patel | 2026-06-24 | 2026-06-24
42 | Punjab Flood Monitoring Meeting MOM | Punjab Flood Monitoring | Done | Medium | — | 2026-06-23 | 2026-06-23
43 | Tender360 V2.4.3 Release | Tender 360 | Done | Medium | Dev Patel | 2026-06-23 | 2026-06-23
44 | Tender360 - Script Enhancement | Tender 360 | Done | Medium | Dev Patel | 2026-06-23 |  | 2026-07-13 06:30
45 | Tender360 Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-22 | 2026-06-23 |  |  | https://cimcondigital.atlassian.net/browse/T3-113 https://cimcondigital.atlassian.net/browse/T3-116 https://cimcondigital.atlassian.net/browse/T3-104 https://cimcondigital.atlassian.net/browse/T3-114 https://cimcondigital.atlassian.net/browse/T3-115 https://cimcondigital.atlassian.net/browse/T3-108
46 | Tender Automation - Ticket Creation | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-22 | 2026-06-22 |  |  | 1. Tender Documents – I have re-uploaded the tender documents. The financial document selection is now correct as per my last observation. However, there is still an issue with the fillable forms — the tool is currently preparing a single form for multiple tender forms. This needs to be resolved at the earliest. 2. Next Upgrade – Experience Document Selection Moving forward, the next enhancement involves the selection of experience documents within the tool. As discussed with both of you, kindly incorporate a toggle-type bar for the following sectors: - Water - Oil & Gas (O&G) - Lighting 3. Document Source – OneDrive Integration The selection of documents should be fetched directly from OneDrive (not from a local server), so that we can use and prepare the documents remotely as needed.
47 | CIMTrack Travel Script Test after production release | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-06-22 | 2026-06-23 |  |  | Please check satya Prakash baghel and kapil dev nigam last 2 days comparison needed for actual travel and our script calculated travel
48 | CMS - Ticket Closing | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-19 | 2026-06-20
49 | TSA - Final Bid grouping testing | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-19 | 2026-06-25 | 2026-06-25 06:30 |  | https://cimcondigital.atlassian.net/browse/TSA-39
50 | Tender360 - Ticket closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-19 | 2026-06-19 |  |  | https://cimcondigital.atlassian.net/browse/T3-110 https://cimcondigital.atlassian.net/browse/T3-104 https://cimcondigital.atlassian.net/browse/T3-115 https://cimcondigital.atlassian.net/browse/T3-100 https://cimcondigital.atlassian.net/browse/T3-111 https://cimcondigital.atlassian.net/browse/T3-112 https://cimcondigital.atlassian.net/browse/T3-107
51 | Tender360 - Corrigendum Documents | Tender 360 | Done | Medium | Dev Patel | 2026-06-18 | 2026-06-18 |  |  | https://cimcondigital.atlassian.net/browse/T3-108
52 | CMS - User Management Automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-17 |  | 2026-06-25 06:30
53 | Tender360 - New ticket creation for the requirements. | Tender 360 | Done | High | Dev Patel | 2026-06-17 | 2026-06-17 |  |  | 1.AOC- winners list 2.prompt - admin control dynamic prompt(setting) 3.status - accept for bidding 4. notification
54 | Tender 360 - Ticket Closing | Tender 360 | Done | Urgent | Dev Patel | 2026-06-17 | 2026-06-17 |  |  | https://cimcondigital.atlassian.net/browse/T3-85 https://cimcondigital.atlassian.net/browse/T3-109 https://cimcondigital.atlassian.net/browse/T3-106 https://cimcondigital.atlassian.net/browse/T3-102 https://cimcondigital.atlassian.net/browse/T3-104
55 | CMS - Production Release | CMS - Urban Voice | Done | High | Harihar Upadhyay | 2026-06-12 |  | 2026-07-13 06:30
56 | Tender360 - Tender scrapping script initial enhancement | Tender 360 | Done | Medium | Dev Patel | 2026-06-12 | 2026-06-12
57 | CMS - Initial Login load testing set up | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-12 | 2026-07-13 | 2026-07-13 06:30
58 | CIMTrack - Geo Tag Testing | CIMTrack | Done | Medium | Rutvik Panchal | 2026-06-03 | 2026-06-04 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-687
59 | TSA - Tickets creation | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-10 | 2026-06-10 |  |  | create ticket for the tickets / points
60 | CIMTrack - give discussion points | CIMTrack | Done | Medium | Rutvik Panchal | 2026-06-10 | 2026-06-10
61 | Tender360 - Ticket creation | Tender 360 | Done | Medium | Dev Patel | 2026-06-10 | 2026-06-10 |  |  | Create all tickets discussed with the himanshu
62 | CIMTrack - Data Migration Validation | CIMTrack Dashboard | Done | Urgent | Sanket Bhimani | 2026-06-06 | 2026-06-06
63 | CMS 2.0 - Iteration 2 Testing | CMS - Urban Voice | Done | Urgent | Harihar Upadhyay | 2026-06-05 | 2026-06-10
64 | Tender360 - Discovered Tender page Testing | Tender 360 | Done | — | Dev Patel | 2026-06-05 | 2026-06-05
65 | Tender360 - Discovered Tender Page Test Case writting | Tender 360 | Done | — | Dev Patel | 2026-06-05 | 2026-06-05
66 | Onboardify - Positive Testing | Tender Submission Automation | Done | — | Viraj Soni | 2026-06-03 | 2026-06-06
67 | Tender 360 - OCR Testing | Tender 360 | Done | Medium | Dev Patel | 2026-06-02 | 2026-06-05 |  |  | https://cimcondigital.atlassian.net/browse/T3-76
68 | CIMTrack New Build Test | CIMTrack | Done | Low | Rutvik Panchal | 2026-05-30 | 2026-06-10 |  |  | 1. mime type change ( should be able to share on teams ) 2. New Message display for multiple try to check-in & check-out ( you have reached your limit message removed)
69 | CIMTrack - 672 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-29 | 2026-06-03 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-672
70 | GMDA Testing & Release | WebScanet - GMDA | On Hold | Medium | — | 2026-05-29
71 | CIMTrack - 684 | CIMTrack | Done | — | Rutvik Panchal | 2026-06-01 |  |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-684
72 | Parvati - iOS testing | Parvati Application | Done | — | Prakash Patel | 2026-05-28 | 2026-05-29
73 | CIMTrack - Distance Script Testing | CIMTrack Dashboard | Done | — | Sanket Bhimani | 2026-05-27 | 2026-06-09
74 | CIMTrack - 683 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-29 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-683
75 | CIMTrack | CIMTrack | Done | Low | Rutvik Panchal | 2026-06-01 |  |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-681
76 | CIMTrack - 682 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-29 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-682
77 | CIMTrack - 679 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-27 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-679?atlOrigin=eyJpIjoiMjc0YjExOGU1MThhNDliNWI1ZjEyMTk1NGRjYzM4ZWEiLCJwIjoiaiJ9
78 | CIMTrack 678 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-27 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-678?atlOrigin=eyJpIjoiNGE5NDRkY2ViZjliNDc0OWI4NDFkNjM5NWI4MjMyNWYiLCJwIjoiaiJ9
79 | Parvati iOS Testing | Parvati Application | Done | — | Prakash Patel | 2026-05-27 | 2026-05-29
80 | Onboadify KT | onboardify 2.0 | Done | — | Shreya Vashishtha | 2026-05-27 | 2026-05-27
81 | CIMTrack Force Password Change | CIMTrack | Done | — | Rutvik Panchal | 2026-05-25 | 2026-05-29
82 | CIMTrack Forgot Password Testing | CIMTrack | Done | — | — | 2026-05-25 | 2026-05-29
83 | CIMTrack Battery Consumption optimization test | CIMTrack | Done | — | — | 2026-05-25 | 2026-06-01 |  |  | Test this for a week with different scenario
84 | Travel Module testing | CIMTrack Dashboard | On Hold | Low | — | 2026-06-03
85 | Tender360 - First Release - V1.0.0 | Tender 360 | Done | — | — | 2026-05-20 | 2026-05-20
86 | CIMTrack - KT | CIMTrack | Done | — | — | 2026-05-20 | 2026-05-20 |  |  | new Distance calculation script KT
87 | TSA all tickets in RFQA | Tender Submission Automation | Done | — | — | 2026-05-20 | 2026-05-29 |  |  | should be able to complete this week or next week.
88 | CIMTrack Ticket verification | CIMTrack | Done | — | — | 2026-05-25 | 2026-05-29
89 | Tender 360 Initial Testing | Tender 360 | Done | — | — | 2026-05-19 | 2026-05-20 |  |  | Test the core functionality and give first release to Marketing team
90 | Parvati KT | Parvati Application | Done | — | — | 2026-05-18 | 2026-05-18 |  |  | give the parvati KT to Gulab bhai
91 | Parvati Release | Parvati Application | Done | — | — | 2026-05-18 | 2026-05-18 |  |  | Revalidate the issue points and retest the application.
92 | User Guide for Expense Module | CIMTrack | Done | — | — | 2026-05-16 | 2026-05-22 |  | User Guide | Create the user guide for the Expense module same as Daily activity
93 | CIMTrack previous Jira Ticket Resolutions | CIMTrack Dashboard | Done | — | — | 2026-05-16 | 2026-05-23 |  |  | https://cimcondigital.atlassian.net/browse/CIMTRACK-594 https://cimcondigital.atlassian.net/browse/CIMTRACK-57 https://cimcondigital.atlassian.net/browse/CIMTRACK-82 https://cimcondigital.atlassian.net/browse/CIMTRACK-106 https://cimcondigital.atlassian.net/browse/CIMTRACK-109 https://cimcondigital.atlassian.net/browse/CIMTRACK-119 https://cimcondigital.atlassian.net/browse/CIMTRACK-121 https://cimcondigital.atlassian.net/browse/CIMTRACK-122 https://cimcondigital.atlassian.net/browse/CIMTRACK-124 https://cimcondigital.atlassian.net/browse/CIMTRACK-125 https://cimcondigital.atlassian.net/browse/CIMTRACK-127 https://cimcondigital.atlassian.net/browse/CIMTRACK-134 https://cimcondigital.atlassian.net/browse/CIMTRACK-141 https://cimcondigital.atlassian.net/browse/CIMTRACK-142 https://cimcondigital.atlassian.net/browse/CIMTRACK-347 https://cimcondigital.atlassian.net/browse/CIMTRACK-348 https://cimcondigital.atlassian.net/browse/CIMTRACK-350 https://cimcondigital.atlassian.net/browse/CIMTRACK-366 https://cimcondigital.atlassian.net/browse/CIMTRACK-370 https://cimcondigital.atlassian.net/browse/CIMTRACK-371 https://cimcondigital.atlassian.net/browse/CIMTRACK-372 https://cimcondigital.atlassian.net/browse/CIMTRACK-378 https://cimcondigital.atlassian.net/browse/CIMTRACK-379 https://cimcondigital.atlassian.net/browse/CIMTRACK-380 https://cimcondigital.atlassian.net/browse/CIMTRACK-397 https://cimcondigital.atlassian.net/browse/CIMTRACK-398 https://cimcondigital.atlassian.net/browse/CIMTRACK-402
94 | No data loss verification | Tender 360 | Done | — | Dev Patel | 2026-05-16 | 2026-05-16 |  | Validation, Manual Testing | once the project is on testing server, validate all 5 dashboards and confirm that there is no data loss.
95 | Tender 360 KT | Tender 360 | Done | — | Dev Patel | 2026-05-16 | 2026-05-18
96 | Test the Expense Voucher Flow | CIMTrack Dashboard | Done | — | — | 2026-05-15 | 2026-06-12 |  |  | Total 264 Test cases are done, now test it.

## Releases
Manual Releases — Total: 12
# | Release Name | Project(s) | Version(s) | Status | Release Date | Manager | Developers
1 | Tender360 - V2.4.5 | Tender 360 | V2.4.5 | Released | 2026-07-09 | Dwip Pandya | Dev Patel
2 | Tender360 - V2.4.4 | Tender 360 | V2.4.4 | Released | 2026-07-03 | Dwip Pandya | Dev Patel
3 | CIMTrack DAR Release | CIMTrack Dashboard | v1.5 | Released | 2026-07-07 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
4 | TSA V2.5.4 | Tender Submission Automation | V2.5.4 | Released | 2026-06-17 | Dwip Pandya | Viraj Soni
5 | Tender 360 Final Release | Tender 360 | V2.4.3 | Released | 2026-06-23 | Dwip Pandya | Dev Patel
6 | CIMTrack Sprint 3 - iOS | CIMTrack | V1.3.5 | Released | 2026-06-16 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
7 | CIMTrack Sprint 3 - Android | CIMTrack | v1.7.1 | Released | 2026-06-16 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
8 | Parvati Release | Parvati Application | V1.0.0 | Released | 2026-06-02 | Dwip Pandya | Prakash Patel
9 | T360 Release | Tender 360 | v1.0.0 | Released | 2026-05-22 | Dwip Pandya | Dev Patel
10 | TSA Initial Release | Tender Submission Automation | v1.0.0 | Released | 2026-04-27 | Dwip Pandya | Viraj Soni
11 | CIMTrack iOS Release | CIMTrack | V1.3.4 | Released | 2026-04-24 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
12 | CIMTrack Android Release | CIMTrack | V1.7.0 | Released | 2026-04-24 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
Release Points — Total: 6
# | Release Point Title | Project(s) | Type | Version(s) | Checklist Progress | Completed
1 | T360 - V2.4.6 | Tender 360 | Past | V2.4.5 (Prev) | 11/11 | Yes
2 | CIMTrack - DAR Report | CIMTrack Dashboard, CIMTrack | Past | — | 11/11 | Yes
3 | Tender360 V2.4.4 | Tender 360 | Past | V2.4.4 (Up) | 11/11 | Yes
4 | TSA V2.2.4 Release | Tender Submission Automation | Past | V2.2.4 (Prev) | 10/10 | Yes
5 | Tender 360 Final Release | Tender 360 | Past | V2.4.3 (Prev) | 20/20 | Yes
6 | CIMTrack Sprint 3 | CIMTrack | Past | Android v1.7.1 (Prev), iOS V1.3.5 (Prev) | 15/15 | Yes

## Test Cases
Test Case Counts by Project
# | Project | Total Test Cases | Not executed | Passed | Failed | Blocked
1 | Savio | 0 | 0 | 0 | 0 | 0
2 | GMDA - JAL Mitra | 0 | 0 | 0 | 0 | 0
3 | NLC Dashboard (Network light control system) | 0 | 0 | 0 | 0 | 0
4 | Engineering Document | 0 | 0 | 0 | 0 | 0
5 | Punjab Flood Monitoring | 0 | 0 | 0 | 0 | 0
6 | GMDA Parvati - Application | 0 | 0 | 0 | 0 | 0
7 | WebScanet - GMDA | 0 | 0 | 0 | 0 | 0
8 | onboardify 2.0 | 0 | 0 | 0 | 0 | 0
9 | Purchase Module | 0 | 0 | 0 | 0 | 0
10 | Tender 360 | 70 | 70 | 0 | 0 | 0
11 | Parvati Application | 129 | 0 | 129 | 0 | 0
12 | Tender Submission Automation | 0 | 0 | 0 | 0 | 0
13 | CMS - Urban Voice | 277 | 0 | 248 | 28 | 1
14 | CIMTrack Dashboard | 386 | 0 | 228 | 41 | 0
15 | CIMTrack | 150 | 4 | 143 | 3 | 0
| TOTAL | 1012 | 74 | 748 | 72 | 1
By Priority
# | Priority | Count
1 | Critical | 0
2 | High | 620
3 | Medium | 375
4 | Low | 17
By Type
# | Type | Count
1 | Manual | 997
2 | Automated | 0
3 | API | 0
4 | Security | 13
5 | Performance | 2
6 | Regression | 0