## Overview
Clair — Project & Executive Task Report
Generated on Wednesday, 23 September 2026 at 5:02 pm
16 | 245 |  | 9 |  | 7 | 2077
PROJECTS | TASKS |  | RELEASES |  | RELEASE POINTS | TEST CASES
Executive Highlights
Task Completion Rate |  | 99% |  | Tasks Completed |  | 243 of 245
Tasks In Progress |  | 0 |  | Active Projects |  | 15 of 16
Releases Logged |  | 9 |  | Test Cases In Scope |  | 2077
Applied Filters & Scope
Projects Scope | All Projects
Developers Scope | All Developers
Date Window | 2026-05-23 to 2026-09-23
Task Status Scope | All Statuses
Release Status Scope | All Statuses
Test Case Scope | All Statuses
Category Breakdown
Projects Portfolio | [5 empty] | 16
Tasks (In Scope) | [5 empty] | 245
Releases Logged | [5 empty] | 9
Release Points | [5 empty] | 7
Test Cases | [5 empty] | 2077

## Projects
# | Project Name | Client | Type | Overall Status | Active Statuses | Assigned Developer(s) | Current Version | Upcoming Version | Completed Tasks | Total Tasks | Task Progress | Last Release | Last Release Date | Description
1 | CIMTrack Dashboard | — | Web | On Going | Testing, Issue Assigned, New Development | Sanket Bhimani, Dwip Pandya | v1.6 | v1.7 | 43 | 44 | 98% | v1.6 released | 2026-08-11 04:10 | —
2 | CIMTrack | — | Mobile App | On Going | Stable, New Development, In Progress | Rutvik Panchal, Dwip Pandya | Android: v1.7.2 iOS: V1.3.6 | Android: v1.7.3 iOS: V1.3.7 | 39 | 39 | 100% | iOS V1.3.6 released | 2026-07-08 11:35 | Android Application
3 | Purchase Module | — | Web | On Going | New Development, In Progress, Testing | Khush Mevada, Dwip Pandya | 1.0.2 | 1.0.3 | 53 | 54 | 98% | — |  | —
4 | Punjab Flood Monitoring | — | Web | On Going | New Development | Harihar Upadhyay, Viraj Soni, Rutvik Panchal, Dwip Pandya, Nilesh Bhil | — | V1.0.0 | 48 | 49 | 98% | — |  | —
5 | SWSM | — | Web | Completed | Started, In Progress | Sanket Bhimani, Dwip Pandya | V2.0.0 | V3.0.0 | 2 | 2 | 100% | — |  | Sanket's SCADA project
6 | General Project | — | Web | On Going | Started, Stable, In Progress | — | — | 0 | 6 | 6 | 100% | — |  | This is a General project which includes all the non project meetings, work and discussions.
7 | Savio | — | Web | On Hold | Yet to Start, N/A | Dwip Pandya | — | V1.0.0 | 1 | 1 | 100% | — |  | A Chatbot project
8 | GMDA - JAL Mitra | — | Mobile App | Yet to Start | — | Prakash Patel, Rutvik Panchal, Dwip Pandya | Android: — iOS: — | Android: V1.0.0 iOS: V1.0.0 | 1 | 2 | 50% | — |  | —
9 | NLC Dashboard (Network light control system) | — | Web | Completed | Testing, In Progress, Automation | Dwip Pandya, Jil Shah | — | V1.0.0 | 14 | 14 | 100% | — |  | —
10 | Engineering Document | — | Web | On Hold | On Hold, In Progress | Viraj Soni, Dwip Pandya | — | N/A | 0 | 0 | 0% | — |  | —
11 | WebScanet - GMDA | — | Web | Completed | Completed | Prakash Patel, Dwip Pandya | — | 3.4.7 | 1 | 1 | 100% | — |  | —
12 | onboardify 2.0 | — | Web | On Hold | On Hold, In Progress | Dwip Pandya | N/A | v1.0.0 | 6 | 6 | 100% | — |  | —
13 | Tender 360 | — | Web | Completed | New Development, Stable, Testing | Dev Patel, Dwip Pandya | V2.4.5 | V2.4.6 | 29 | 29 | 100% | V2.4.5 released | 2026-07-09 11:35 | —
14 | Parvati Application | — | Mobile App | Completed | Stable | Prakash Patel, Dwip Pandya | Android: V1.0.0 iOS: V1.0.0 | Android: V1.0.1 iOS: V1.0.1 | 4 | 4 | 100% | — |  | Web view in mobile.
15 | Tender Submission Automation | — | Web | Completed | Testing, In Progress | Viraj Soni, Dwip Pandya | V2.2.4 | V2.5.4 | 8 | 8 | 100% | V2.5.3 released | 2026-06-23 11:39 | —
16 | CMS - Urban Voice | — | Web | Completed | Stable, Completed, Blocker | Harihar Upadhyay, Dwip Pandya | V1.0.0 | v2.0.0 | 15 | 15 | 100% | — |  | —

## Tasks
# | Task Name | Project(s) | Status | Priority | Developer(s) | Start Date | End Date | Completed Date | Work Done | Description | Tags
1 | Punjab flood: discuss the found issue with harihar | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-09-22 | 2026-09-22 | 2026-09-22 06:30 | — | — | —
2 | Purchase module - CI/CD implementation discussion with khush | Purchase Module | To-Do | Medium | Khush Mevada | 2026-09-22 | 2026-09-23 |  | — | — | —
3 | CIMTrack - Requirement document reading and analysis | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani | 2026-09-22 | 2026-09-23 | 2026-09-22 06:30 | Gone through the complete 75 Paged SRS document shared by sanket for the new CIMTrack functionality, understood the flow and required changes, discussed with sanket regarding few doubts and then created a simple documents which mentioned the complete flow of the functionality, step by step guide and explanation along with QA scenarios and required validation in this functionality. Send a mail to lokesh ji so that he can understand the flow in simpler manner | — | —
4 | Purchase module - Allure report configuration in playwright | Purchase Module | Done | Medium | Khush Mevada | 2026-09-19 | 2026-09-22 | 2026-09-21 06:30 | - Configured and integrated Allure Interactive Reporting into the Playwright automation framework. - Set up and verified the required local Java environment variables and Allure report compilation commands. - Automated report generation and test artifact archiving within the GitHub Actions CI/CD pipeline for both pull requests and main branch deployments. - Documented the complete Allure report execution workflow, including commands, setup steps, and usage instructions. | — | —
5 | Rating Curve Discussion | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-09-18 | 2026-09-19 | 2026-09-21 06:30 | Analyzed the existing Rating Curve download functionality and discussed the required download format. Finalized the expected format and discussed the identified issues related to the Rating Curve download output. | — | —
6 | Purchase module - API Testing setup | Purchase Module | Done | Medium | Khush Mevada | 2026-09-18 | 2026-09-22 | 2026-09-21 06:30 | Set up the API automation environment for the Purchase Module and reviewed the available APIs to gain an overall understanding of the API structure and functionality. | — | —
7 | Purchase module - CI/CD Implantation Phase 3 | Purchase Module | Done | Medium | Khush Mevada | 2026-09-21 | 2026-09-23 | 2026-09-21 06:30 | Engineered an autonomous self-healing rollback engine using GitHub Actions & GitHub CLI (`gh workflow run`) that automatically reverts broken commits on main (`git revert HEAD`), restores clean code, and re-dispatches pipeline runs without human intervention. | Implement the self healing CI/CD | —
8 | Purchase module - CI/CD Implantation Phase 2 | Purchase Module | Done | Medium | Khush Mevada | 2026-09-21 | 2026-09-23 | 2026-09-21 06:30 | - Implemented an 80% passing boundary metric evaluator that halts the pipeline and blocks Vercel deployment if test compliance drops below 80.00%. | Implement the percentage thresholds | —
9 | Purchase module - CI/CD Implantation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-21 | 2026-09-23 | 2026-09-21 06:30 | - Designed a 3-stage quality gate enforcing ESLint static code analysis, Vite build compilation, and 53 Playwright E2E browser test scenarios. | Implement the CI/CD in the Purchase module automation test cases. | —
10 | Proper documentation of komal ma'am requirement | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-17 | 2026-09-17 | 2026-09-17 06:30 | — | — | —
11 | Punjab Flood monitoring : create jira tickets for all the requirements. | Purchase Module | Done | Medium | Khush Mevada | 2026-09-17 | 2026-09-18 | 2026-09-17 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-185 https://cimcondigital.atlassian.net/browse/P4PFM-186 https://cimcondigital.atlassian.net/browse/P4PFM-187 https://cimcondigital.atlassian.net/browse/P4PFM-188 https://cimcondigital.atlassian.net/browse/P4PFM-189 https://cimcondigital.atlassian.net/browse/P4PFM-190 https://cimcondigital.atlassian.net/browse/P4PFM-191 https://cimcondigital.atlassian.net/browse/P4PFM-192 https://cimcondigital.atlassian.net/browse/P4PFM-193 https://cimcondigital.atlassian.net/browse/P4PFM-194 https://cimcondigital.atlassian.net/browse/P4PFM-195 https://cimcondigital.atlassian.net/browse/P4PFM-196 https://cimcondigital.atlassian.net/browse/P4PFM-197 https://cimcondigital.atlassian.net/browse/P4PFM-198 https://cimcondigital.atlassian.net/browse/P4PFM-199 | — | —
12 | Purchase module - API understanding with khush | Purchase Module | Done | Medium | Khush Mevada | 2026-09-17 | 2026-09-18 | 2026-09-17 06:30 | — | — | —
13 | Purchase module - Manual Testing of HR & Admin module | Purchase Module | Done | Medium | Khush Mevada | 2026-09-17 | 2026-09-18 | 2026-09-18 06:30 | — | — | —
14 | Purchase module automation test case audit | Purchase Module | Done | Medium | Khush Mevada | 2026-09-16 | 2026-09-16 | 2026-09-16 06:30 | performed audit manually and using AI as well, and identified all the missing points and strengths. | — | —
15 | Punjab flood - Create the new enhancement ticket | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-09-16 | 2026-09-06 | 2026-09-16 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-178 https://cimcondigital.atlassian.net/browse/P4PFM-179 https://cimcondigital.atlassian.net/browse/P4PFM-180 https://cimcondigital.atlassian.net/browse/P4PFM-181 https://cimcondigital.atlassian.net/browse/P4PFM-182 https://cimcondigital.atlassian.net/browse/P4PFM-183 https://cimcondigital.atlassian.net/browse/P4PFM-184 | — | —
16 | Purchase module : Admin Dashboard -> User verification flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-15 | 2026-09-15 | 2026-09-15 06:30 | Automated the complete user verification journey where a newly created user's information is validated across the management table. The test then opens the user's edit dialog to confirm that all previously assigned details—such as username, email, full name, role, reporting manager, assigned divisions, blank password state, and active toggle settings—are accurately preserved and displayed correctly. | — | —
17 | Purchase module : Admin Dashboard -> Edit User flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-15 | 2026-09-17 | 2026-09-16 06:30 | automated the end-to-end user edit and deactivation lifecycle in the Admin module. First, I captured the initial dashboard user metrics, created a new user, and verified their initial data in the user management table. Then, I opened the Edit User modal to update the user details (first name, last name, and email), toggled the user activation switch to deactivate them, and submitted the update while validating the "User updated successfully" toast. Finally, I verified that the table status updated to "Access revoked" and validated the dashboard metrics across all stages to ensure the total, active, and deactivated user counts accurately reflected the change. | Edit the user and validate the data | —
18 | Purchase module : Admin Dashboard -> User activation flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-15 | 2026-09-17 | 2026-09-16 06:30 | automated the authentication and permission validation flow for active versus inactive users. I first created a new active user with the "Admin" role, logged out from the admin account, and successfully logged in using the newly created user's credentials to verify that all 9 primary navigation modules (Requisitions, Store, Purchase, Manufacturing Order, Vendor, Components, Quality, HR & Administration, and Admin) were visible. Afterward, I logged back into the admin account, edited the created user to toggle their active status off (deactivate them), saved the update, and logged out. Finally, I attempted to log in with the deactivated user's credentials and verified that access was blocked with an error alert, ensuring inactive users cannot access the system. | Validate that active user can login and deactive user can not. | —
19 | Purchase module : Admin Dashboard -> User Validation flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-15 | 2026-09-15 | 2026-09-15 06:30 | In the User Validation flow, we opened the Create User form and submitted it empty to verify the error alert toast and all five required inline validation messages, then filled in each field one by one to ensure the error messages cleared dynamically in real time, and finally submitted the completed form to verify the user creation toast, the user's presence in the table, and the user count increment on the dashboard. | — | —
20 | Purchase module : Admin Dashboard -> Delete User flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-15 | 2026-09-15 | 2026-09-15 06:30 | Revoke User Access Flow: Automated the access revocation flow, including the confirmation modal, success toast, table status update to "Access revoked", removal of the delete button, and disabled status toggle in the edit modal. | — | —
21 | Purchase module : Admin Dashboard -> Add User flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-15 | 2026-09-15 | 2026-09-15 06:30 | Add User Flow: Automated empty form validation (error toast and 5 inline error messages), dynamic error clearing upon typing, user creation, table verification, and dashboard user count increase (+1). | — | —
22 | Purchase module : Admin Dashboard -> User Management Data Validation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-15 | 2026-09-15 | 2026-09-15 06:30 | Done | Get the table data and all locator data. | —
23 | Purchase module : Admin Dashboard data gathering automation | Purchase Module | Done | Medium | Khush Mevada | 2026-09-15 | 2026-09-15 | 2026-09-15 06:30 | Automation flow completed. | — | —
24 | CIMTrack - Installation activity bug root cause analysis - initial fix testing - Dasboard | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-09-11 | 2026-09-11 | 2026-09-11 06:30 | Tested it after the Release of front-end and backend from developer. | — | —
25 | CIMTrack - Installation activity bug root cause analysis - initial fix testing - Mobile application | CIMTrack | Done | Medium | Rutvik Panchal | 2026-09-11 | 2026-09-11 | 2026-09-11 06:30 | - Initial submit issue has been fixed - still the issue is in when no instrument description was added, then the instrument remark is being displayed same as activity description. - the update issue is still there in which rutvik and sanket are working on. | — | —
26 | CIMTrack - Installation activity bug root cause analysis | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-11 | 2026-09-11 | 2026-09-11 06:30 | - Root cause analysis for the daily activity module's installation activity issue about the description mis-match and auto filling and issue while updating the daily activity. - Discussed about the issue with sanket and rutvik along with that found the root cause analysis about the issue and discuss the possible solutions | — | —
27 | Punjab Client tranining meeting | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Viraj Soni, Rutvik Panchal, Nilesh Bhil | 2026-09-11 | 2026-09-11 | 2026-09-11 06:30 | Done, total 2.5hr of meeting. | — | —
28 | CIMTrack Sprint creation | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-10 | 2026-09-15 | 2026-09-15 06:30 | Sprint URC created along with the tickets : https://cimcondigital.atlassian.net/browse/CIMTRACK-747 https://cimcondigital.atlassian.net/browse/CIMTRACK-748 https://cimcondigital.atlassian.net/browse/CIMTRACK-749 https://cimcondigital.atlassian.net/browse/CIMTRACK-750 https://cimcondigital.atlassian.net/browse/CIMTRACK-751 https://cimcondigital.atlassian.net/browse/CIMTRACK-752 https://cimcondigital.atlassian.net/browse/CIMTRACK-753 | — | —
29 | User Management - Automation Locator gathering | Purchase Module | Done | Medium | Khush Mevada | 2026-09-10 | 2026-09-19 | 2026-09-15 06:30 | Done and added the file structure as well | Gather all the locators from the admin dashboard's user management | —
30 | Admin Dashboard - Automation Locator gathering | Purchase Module | Done | Medium | Khush Mevada | 2026-09-10 | 2026-09-19 | 2026-09-15 06:30 | Done and added the file structure as well | Gather all the locators from the admin dashboard | —
31 | Enhancement review | CIMTrack | Done | Medium | Rutvik Panchal | 2026-09-10 | 2026-09-10 | 2026-09-10 06:30 | discussed and verified the GEO-tagged image verification and DAR updates. | verified the new enhancement for the cimtrack application | —
32 | requirement point discussion | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-10 | 2026-09-10 | 2026-09-10 06:30 | completed, discussion done. | requirement point discussion with sanket | —
33 | CIMTrack KT | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-10 | 2026-09-10 | 2026-09-10 06:30 | Given completed KT to komal ma'am | Give Komal ma'am an overview of CIMTrack from Scratch | —
34 | Create the requirement tickets | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-10 | 2026-09-10 | 2026-09-10 06:30 | https://cimcondigital.atlassian.net/browse/CIMTRACK-747 https://cimcondigital.atlassian.net/browse/CIMTRACK-748 https://cimcondigital.atlassian.net/browse/CIMTRACK-749 https://cimcondigital.atlassian.net/browse/CIMTRACK-750 https://cimcondigital.atlassian.net/browse/CIMTRACK-751 https://cimcondigital.atlassian.net/browse/CIMTRACK-752 https://cimcondigital.atlassian.net/browse/CIMTRACK-753 | create the tickets for the requirements discussed during the meeting with Komal ma'am | —
35 | Meeting with komal ma'am | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-10 | 2026-09-10 | 2026-09-10 06:30 | Meeting done | Meeting with komal ma'a regarding the jutan sir's mail about the image validation | —
36 | CIMTrack Meeting organized by Komal ma'am | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-08 | 2026-09-08 | 2026-09-08 06:30 | — | — | —
37 | T360 Testing for darshak sir's requirement. | Tender 360 | Done | Medium | Dev Patel | 2026-09-07 | 2026-09-07 | 2026-09-07 06:30 | Ticket : https://cimcondigital.atlassian.net/browse/T3-164 verified : Performed functional and regression testing for the **Accepted for Bidding** workflow, including tender assignment, submission, tracking, and role-based access for Proposal Team Members. Verified tender visibility, status updates, and existing functionality across relevant Tender360 screens. | — | —
38 | verified and closed the rate limit display issue. | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-07 | 2026-09-07 | 2026-09-07 06:30 | https://cimcondigital.atlassian.net/browse/CIMTRACK-746 - verified and closed | — | —
39 | Create the Rate limit display bug ticket | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-09-07 | 2026-09-07 | 2026-09-07 06:30 | https://cimcondigital.atlassian.net/browse/CIMTRACK-746 | — | —
40 | Automation script updation | General Project | Done | Medium | — | 2026-09-07 | 2026-09-07 | 2026-09-07 06:30 | 1. Developed an automation script to configure the lograte of live RTUs across PNC, Hathras, Afcon, and Anutech sites. 2. The script automatically sets the lograte to 60 for all applicable live RTUs and generates a report containing the execution and configuration results. | update the new live rtu devices and set lograte to 60 | —
41 | Datasheet logic enhancement | General Project | Done | Medium | — | 2026-09-07 | 2026-09-09 | 2026-09-08 06:30 | automated our Site Commissioning workbook so Client_Report stays in sync with Site Master. Every report layout now pulls its data by Node No. via INDEX/MATCH, so editing the master updates the report instantly, and I added a Google Apps Script that creates a fresh 50-row layout whenever a new Node No. is entered. I also consolidated everything into one Google workbook - Setup, Dashboard, Site Master and Client_Report — and filled in the 11 layouts that were missing. I verified the data and the automation with Gulab bhai, and shared the workbook with him after verification. | Gulab bhai task. | —
42 | Prepare the workdone Vs project requirement in punjab project. | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Viraj Soni, Rutvik Panchal, Nilesh Bhil | 2026-09-07 | 2026-09-07 | 2026-09-07 06:30 | - Worked on documentation for the Punjab Flood Monitoring System project. Reviewed and updated the final delivery report based on the latest status inputs from the team. - Also prepared a separate two-page additional work document summarising everything delivered beyond the original tender scope, covering dashboard enhancements, alert and notification improvements, reporting features, mobile app additions, backend and infrastructure work, and system administration capabilities. Written in plain format for sharing with the client or internal stakeholder | — | —
43 | Automation script | General Project | Done | Medium | — | 2026-09-02 | 2026-09-02 | 2026-09-02 06:30 | 1. Developed an automation script to configure the lograte of live RTUs across PNC, Hathras, Afcon, and Anutech sites. 2. The script automatically sets the lograte to 15 for all applicable live RTUs and generates a report containing the execution and configuration results. | write automation script to set the log rate of all the live rtu devices in PNC, Hathras, Afcon, and Anutech. | —
44 | Prepare SRS for new requirement | SWSM | Done | Medium | Sanket Bhimani | 2026-09-02 | 2026-09-02 | 2026-09-02 06:30 | Done, verified with sanket mail sent. | — | —
45 | Manual Testing | Purchase Module | Done | Medium | Khush Mevada | 2026-09-02 | 2026-09-02 | 2026-09-02 06:30 | — | do the manual testing of the indent process and project creation. | —
46 | Sanity Test | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-09-02 | 2026-09-02 | 2026-09-02 06:30 | — | Do the sanity testing in Harihar's local env to validate that software is working. | —
47 | Bug communication | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-31 | 2026-09-03 | 2026-09-01 06:30 | — | 1. communicate with Sanket regarding the bug in analytics dashboard, and Nisha ma'am Forgot to punch in on 31st Aug. and it was Monday, still CIMTrack displays the long abs. for the selected week. 2. discuss for the Data quality flag for me cause i logged all 7h and 30m in one day for one project | —
48 | RFQA Ticket closing | Purchase Module | Done | Medium | Khush Mevada | 2026-08-31 | 2026-09-01 | 2026-09-01 06:30 | All verified and closed. | https://cimcondigital.atlassian.net/browse/PA-301 https://cimcondigital.atlassian.net/browse/PA-302 https://cimcondigital.atlassian.net/browse/PA-305 https://cimcondigital.atlassian.net/browse/PA-306 | —
49 | Update the Toast messages | Purchase Module | Done | Medium | Khush Mevada | 2026-08-31 | 2026-08-31 | 2026-08-31 06:30 | updated in all the test case spec file. | update the toast messages in the validated file cause the toast messages has been updated for few. | —
50 | Extra enhancements of Vendor automation flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-31 | 2026-08-31 | 2026-08-31 06:30 | 1. Document Availability & Download Validation : I enhanced how the system handles vendor documents by testing different document availability scenarios. I validated that vendors with complete sets of documents display active download options for each certificate, while optional missing documents clearly display an unavailable indicator instead of broken download links. I also simulated clicking through each available document download to ensure the system processes them correctly and logs every action. 2. Randomized Document Uploads & MSME Handling : To make our testing closer to real-world usage, I introduced intelligent randomization during vendor onboarding. The system now randomly decides whether a business is registered under MSME and automatically handles the required certificates accordingly. Additionally, optional files like incorporation certificates and tax allotment letters are now randomly uploaded—either both, just one, or none at all—to thoroughly test all possible onboarding combinations. 3. Approval Queue Document Counts & Badge Tracking : I implemented precise document count and status tracking in the approval screen. When reviewing a pending vendor, the system now calculates the exact ratio of uploaded documents against total expected requirements, updating the count from both the main table badge and inside the detailed review popup. I also verified that each certificate accurately reflects its status with a green download badge when available or a red missing indicator when omitted. 4. Comprehensive Vendor Module Documentation : I created an extensive and well-organized master guide for the entire vendor module. This document outlines the responsibilities of different user roles, maps out all the user journeys from initial registration to final approval, details every form rule and system message, and serves as a complete reference for anyone exploring or reviewing our automation coverage. | — | —
51 | Vendor - Document count validation automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-31 | 2026-08-31 | 2026-08-31 06:30 | I enhanced how the system handles vendor documents by testing different document availability scenarios. I validated that vendors with complete sets of documents display active download options for each certificate, while optional missing documents clearly display an unavailable indicator instead of broken download links. I also simulated clicking through each available document download to ensure the system processes them correctly and logs every action. | — | —
52 | Vendor management - all test cases | Purchase Module | Done | Medium | Khush Mevada | 2026-08-31 | 2026-09-01 | 2026-08-31 06:30 | Total 143 Test cases created and added in the test case management | Complete all the test cases of vendor module including the normal flow and account flow. | —
53 | project creation automation creation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-31 | 2026-09-01 | 2026-09-01 06:30 | - Automated New Project Creation Flow : uilt test automation for creating projects under Requisition Indents, covering required field validations, incremental form filling, and duplicate project code checks. - Strict Toast & Alert Verification: Added exact matching for all system notifications (successful project creation, duplicate alerts, and form reset confirmations). - Automated Table & Data Persistence Verification: Built end-to-end verification that creates a project, reloads the page, opens the All Projects modal, verifies all table column headers, searches the created project, and validates each data cell against the entered values. - Automated Project Selection: Verified selecting the created project from the table and ensuring the form populates accurately. - Implemented Structured Execution Logging: Added clean, step-by-step console logs displaying all form inputs, table data, and phase results during test runs. | — | —
54 | Duplicate Vendor Registration validation automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-29 | 2026-08-29 | 2026-08-31 06:30 | — | — | —
55 | Onboardify - Complete full automation of onboardify | onboardify 2.0 | Done | Medium | — | 2026-08-29 | 2026-08-29 | 2026-08-29 06:30 | Designed, implemented, and verified an end-to-end QA automation test framework for Onboardify 2.0 using Playwright, TypeScript, and Page Object Model (POM). Automated the critical business workflows across HR Admin and Employee roles, including multi-step onboarding (Steps 0–5), document upload flows (Photo, Bank Proof, Aadhar, PAN, Educational degrees), Employee CRUD, welcome email credential generation, and cross-role lifecycle verification. Enhanced the framework with dynamic dashboard metric card validations (verifying increment/decrement of Total, Pending, and Completed cards on create, delete, and completion actions), execution pacing with slowMo & deliberate phase timeouts for human-observable headed runs, and comprehensive test suite documentation in the README. Successfully validated the entire suite with a 100% pass rate (11/11 tests passing). | — | —
56 | Onboardify - Employee Portal automation | onboardify 2.0 | Done | Medium | — | 2026-08-29 | 2026-08-29 | 2026-08-29 06:30 | Designed, implemented, and verified an end-to-end QA automation test framework for Onboardify 2.0 using Playwright, TypeScript, and Page Object Model (POM). Automated the critical business workflows across HR Admin and Employee roles, including multi-step onboarding (Steps 0–5), document upload flows (Photo, Bank Proof, Aadhar, PAN, Educational degrees), Employee CRUD, welcome email credential generation, and cross-role lifecycle verification. Enhanced the framework with dynamic dashboard metric card validations (verifying increment/decrement of Total, Pending, and Completed cards on create, delete, and completion actions), execution pacing with slowMo & deliberate phase timeouts for human-observable headed runs, and comprehensive test suite documentation in the README. Successfully validated the entire suite with a 100% pass rate (11/11 tests passing). | Automate the complete Employee admin functionalities | —
57 | Onboardify - HR Portal automation | onboardify 2.0 | Done | Medium | — | 2026-08-29 | 2026-08-29 | 2026-08-29 06:30 | Designed, implemented, and verified an end-to-end QA automation test framework for Onboardify 2.0 using Playwright, TypeScript, and Page Object Model (POM). Automated the critical business workflows across HR Admin and Employee roles, including multi-step onboarding (Steps 0–5), document upload flows (Photo, Bank Proof, Aadhar, PAN, Educational degrees), Employee CRUD, welcome email credential generation, and cross-role lifecycle verification. Enhanced the framework with dynamic dashboard metric card validations (verifying increment/decrement of Total, Pending, and Completed cards on create, delete, and completion actions), execution pacing with slowMo & deliberate phase timeouts for human-observable headed runs, and comprehensive test suite documentation in the README. Successfully validated the entire suite with a 100% pass rate (11/11 tests passing). | Automate the complete HR admin functionalities | —
58 | Ticket creation for vendor file download bug | Purchase Module | Done | Medium | Khush Mevada | 2026-08-29 | 2026-08-29 | 2026-08-29 06:30 | https://cimcondigital.atlassian.net/browse/PA-302 | — | —
59 | vendor - download & Export validation and automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-27 | 2026-08-30 | 2026-08-29 06:30 | found one bug and created ticket for that | — | —
60 | Vendor - Filter automation flow and validation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-27 | 2026-09-04 | 2026-08-31 06:30 | - I built and verified comprehensive filtering for our vendor database. I ensured that we can easily filter vendors by their lifecycle statuses—such as pending, approved, or rejected—as well as by product categories and document availability. I also validated that combining search keywords with active filters works smoothly, handles empty states gracefully without crashing the table, and allows users to export the filtered vendor list with immediate confirmation. | — | —
61 | Vendor - Full lifecycle automation using playwright | Purchase Module | Done | Medium | Khush Mevada | 2026-08-27 | 2026-08-27 | 2026-08-27 06:30 | — | include all the existing test cases and create one consolidated spec test cases which includes all. | —
62 | Vendor - PO Generation dropdown validation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-27 | 2026-08-27 | 2026-08-27 06:30 | Implemented the new vendor flow of verificaion in the Purchase section's Master database's PO generate. verified the before and after vendor approval flow. to make this automated i gathered all the locators using playwright codegen and structured the locators accoding to POM. | — | —
63 | Vendor database approval & rejection flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-26 | 2026-08-26 | 2026-08-26 06:30 | - Automated Accounts Team Vendor Approval Workflow: Created a dedicated automated test for the Accounts team approval flow where an Accounts user logs in, locates the approved vendor in the database directory, opens the confirmation dialog, approves the vendor, and verifies the status chip updates. - Automated Accounts Team Vendor Rejection Workflow: Created a dedicated automated test for the Accounts team rejection flow where an Accounts user logs in, locates the vendor in the database directory, opens the rejection modal, submits mandatory rejection remarks, and verifies status updates. | — | —
64 | Vendor Database module automation set up | Purchase Module | Done | Medium | Khush Mevada | 2026-08-26 | 2026-08-26 | 2026-08-26 06:30 | all locators gathered. and flow was created | get all the locators, and set up the flow | —
65 | Account approval - Vendor flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-26 | 2026-08-26 | 2026-08-26 06:30 | I implemented dynamic conditional automation logic for the Vendor Database that inspects live table records and automatically executes either an approval or rejection workflow based on the current status of the first database entry. When the first record is pending, the automation logs out via the user profile avatar menu, logs in as the Accounts team, approves the vendor through the confirmation modal, and verifies the updated approval status badge; if the first record is already processed, the system automatically scans down the table to locate an actionable pending vendor, logs in as Accounts, submits mandatory rejection reasons, and confirms the rejected status badge. Finally, the workflow logs back in under the Developer role to verify that all status updates made by the Accounts team accurately sync and display across the platform in real time. | — | —
66 | Search Edge-cases automation in vendor | Purchase Module | Done | Medium | Khush Mevada | 2026-08-25 | 2026-08-25 | 2026-08-25 06:30 | — | — | —
67 | Vendor automation for file validation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-25 | 2026-08-25 | 2026-08-25 06:30 | — | — | —
68 | Tender 360 - New functionality validation | Tender 360 | Done | Medium | Dev Patel | 2026-08-25 | 2026-09-04 | 2026-09-01 06:30 | — | validate that a new page and sidebar menu has been added in Darshak sir's dashboard | —
69 | Tender360 - new data validation | Tender 360 | Done | Medium | Dev Patel | 2026-08-25 | 2026-09-04 | 2026-09-01 06:30 | — | Validate that no tenders that have already been accepted are still being displayed on Darshak Sir’s dashboard. | —
70 | Account team Vendor approval flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-25 | 2026-08-27 | 2026-08-26 06:30 | Implemented | implement the automation for the vendor approval from the account team. | —
71 | Vendor testcase sheet | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-25 | 2026-08-25 06:30 | Creates new testcase sheet and total 86 test cases. uploaded the sheet in testcase management as well. | create a test case excel sheet for the vendor module of purchase module | —
72 | Full vendor workflow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-24 | 2026-08-24 06:30 | - Completed the full 10-phase Vendor Lifecycle test covering vendor registration, approval, rejection, editing, document re-upload, re-approval, and final approval. Added checks for all required tabs, modals, fields, documents, and empty states. Updated vendor locators, added standard logs across all 8 test files, configured Playwright to run tests sequentially to avoid backend issues, and updated the README with the test structure, cases, and execution steps. | — | —
73 | Edit vendor automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-24 | 2026-08-24 06:30 | - Implemented the end-to-end Vendor Information Edit and cross-page verification test suite. The test registers a vendor dynamically, searches and opens the Edit modal on /vendor-edit, performs strict 13-field pre-filled checks, updates all form fields & document attachments, re-opens the Edit modal post-submit to verify persisted data, and navigates to /vendor-approval to confirm all updated details and documents match inside the View Details modal. | — | —
74 | Vendor registration validation automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-24 | 2026-08-24 06:30 | Implemented a complete incremental field-by-field validation test for Vendor Registration following standard Page Object Model guidelines. The test verifies initial empty form error states across all mandatory fields, confirms field errors clear as each input is filled, validates document error toasts, and completes registration with dynamic attachments and URL endpoint assertions. | — | —
75 | Vendor Conditional approval flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-24 | 2026-08-24 | 2026-08-24 06:30 | Created automated test suite covering Vendor Approval and Rejection actions triggered directly from inside the View Details modal. | — | —
76 | Vendor Validation automation flow | Purchase Module | Done | Medium | Khush Mevada | 2026-08-21 | 2026-08-21 | 2026-08-21 06:30 | - Vendor Verification Execution: Ran the Vendor Verification end-to-end test suite in headed mode. - Data & Modal Accuracy Verification: Confirmed that all registered vendor details (Header Name, Contact Person, Category, MSME status, Website, Address) and all 7 uploaded document download buttons were accurately displayed in the View Details modal. - Verification Result: The test suite executed and passed cleanly. | — | —
77 | Vendor Rejection flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-21 | 2026-08-21 06:30 | - Vendor Rejection Test Flow: Created an end-to-end test suite that checks for pending vendors in the queue, or registers a new vendor if the queue is empty. - Rejection Modal & Remarks: Opens the rejection modal, fills dummy rejection remarks, and confirms vendor rejection. - Toast Message Assertion: Verifies the "Vendor rejected successfully" toast alert. - URL Endpoint Assertions: Validates page endpoints upon every navigation transition. - Pending Count Verification: Reloads the page and verifies the pending queue count decreases by 1 ($1 \rightarrow 0$). - Verification: Successfully executed and passed the test in headed mode. | — | —
78 | Vendor view data validation automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-21 | 2026-08-21 06:30 | - Vendor Verification Execution: Ran the Vendor Verification end-to-end test suite in headed mode. - Data & Modal Accuracy Verification: Confirmed that all registered vendor details (Header Name, Contact Person, Category, MSME status, Website, Address) and all 7 uploaded document download buttons were accurately displayed in the View Details modal. - Verification Result: The test suite executed and passed cleanly. | — | —
79 | Vendor approval flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-21 | 2026-08-21 06:30 | -Vendor Approval Page Object: Created locators and helper actions for the table, search, view details modal, rejection modal, and approve confirmation modal using data-testid attributes. - Smart Approval Test Flow: Created an end-to-end test that checks for existing pending vendors to approve, or registers a new vendor if the queue is empty, then approves and verifies the pending count decreases by 1 after page reload. - URL Endpoint Validation: Added explicit URL endpoint assertions on every page navigation across all test flows. - Standardized Step Logging: Added JSDoc header descriptions, numbered steps, emojis, and console logs across all test suites. - Execution & Config Tuning: Configured 500ms action delay (slowMo) and 50-second test timeouts for reliable visual test execution. - Verification: Successfully executed and passed all tests in headed mode. | — | —
80 | Vendor Registration flow automation | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-20 | 2026-08-20 06:30 | - Built locators and fillVendorRegistrationForm() for all form fields, dropdowns, and document uploads - Created auto-generating unique test data using timestamps and generic "Test" names so tests run repeatedly without manual updates. - Written VendorRegistration.spec.ts with test.step() blocks, exact toast message validation | — | —
81 | Login test suit for the different roles | Purchase Module | Done | Medium | Khush Mevada | 2026-08-20 | 2026-08-20 | 2026-08-20 06:30 | Created a reusable loginAs(page, role) helper function and updated all module endpoints | — | —
82 | Locator extractions | Purchase Module | Done | Medium | — | 2026-08-19 | 2026-08-20 | 2026-08-20 06:30 | — | Extract the locators from the purchase module login and dashboard | —
83 | Close RFQA Tickets for punjab project | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal | 2026-08-19 | 2026-08-20 | 2026-09-15 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-163 https://cimcondigital.atlassian.net/browse/P4PFM-177 | — | —
84 | Prepare a test planning for modules | Purchase Module | Done | Medium | Khush Mevada | 2026-08-18 | 2026-08-25 | 2026-08-24 06:30 | 1. Vendor 2. Requisition 3. Component 4. Store 5. Purchase & MO 6. Quality Admin module is not fixed | prepare the test planning for the purchase module sub modules | —
85 | Prepare understanding flow document for purchase module | Purchase Module | Done | Medium | Khush Mevada | 2026-08-18 | 2026-08-19 | 2026-08-19 06:30 | Prepared the flow chart and shared with disha and khush for the review | — | —
86 | Purchase module KT | Purchase Module | Done | Medium | Khush Mevada | 2026-08-18 | 2026-08-18 | 2026-08-18 06:30 | Took KT with disha and khush | — | —
87 | CIMTrack - plot google maps | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-18 | 2026-08-18 | 2026-08-18 06:30 | Plotted all map and shared with komal ma'am | plot the google map for the Dhruv krishna's distances for 03-04-26, 20-06-2026, 14-05-26, 20-05-26 | —
88 | Document go through | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 | Went through the documents | go through the mail sanket shared and do a brainstorming for the new functionality | —
89 | Punjab flood - ML logic document updation | Punjab Flood Monitoring | Done | Medium | Viraj Soni | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 | Sat with viraj and understood the flow and updated the document. | do a discussion with viraj and verify that do we actually take the travel distance and travel time given in the line diagram to train the ML modal | —
90 | Close Application RFQA tickets | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 | - Ticket can not be closed as ticket has one bug - https://cimcondigital.atlassian.net/browse/P4PFM-174 : bug reported and explained to rutvik | - https://cimcondigital.atlassian.net/browse/P4PFM-155 - Close the RFQA ticket. | —
91 | Punjab flood - Sanity Test | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 | Completed the sanity test and no major issues were found only the minor issues which are already assigned. | Do a sanity test in the QA instance | —
92 | Punjab flood - Data flow validation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-17 | 2026-08-17 | 2026-08-17 06:30 | New line diagram has been given by the client so we have to re-validate it once development is completed. | Validate the data indexing performed by harihar based on shared line diagram | —
93 | Punjab flood - KT session for edit functionality | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-17 | 2026-08-18 | 2026-08-18 06:30 | KT done | — | —
94 | Document go-through | Punjab Flood Monitoring | Done | Medium | Viraj Soni | 2026-08-13 | 2026-08-13 | 2026-08-13 06:30 | — | Go through the documents of prediction modal with viraj and get as much info as possible. | —
95 | Close new RFQA tickets - punjab flood | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-13 | 2026-08-13 | 2026-08-13 06:30 | - Tested Site Type filtering for River, Headworks, and Site with existing site, jurisdiction, and permission filters. - Tested All Site assignment with jurisdiction override and restoration of existing jurisdiction rules after removal. - Tested Feet/Meter water level conversion in the Add Reading form, including accurate conversion and submission. https://cimcondigital.atlassian.net/browse/P4PFM-164 https://cimcondigital.atlassian.net/browse/P4PFM-166 https://cimcondigital.atlassian.net/browse/P4PFM-158 | — | —
96 | New Requirement Ticket generation for Punjab project | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal | 2026-08-14 | 2026-08-14 | 2026-08-14 06:30 | Rutvik Panchal https://cimcondigital.atlassian.net/browse/P4PFM-167 - Site type Filter https://cimcondigital.atlassian.net/browse/P4PFM-170 - Display discharge column https://cimcondigital.atlassian.net/browse/P4PFM-172 - Internal color code Harihar Upadhyay https://cimcondigital.atlassian.net/browse/P4PFM-168 - River basin column https://cimcondigital.atlassian.net/browse/P4PFM-169 - Display discharge column https://cimcondigital.atlassian.net/browse/P4PFM-171 - Internal color code | — | —
97 | CIMTrack - document go through | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-12 | 2026-08-12 | 2026-08-12 06:30 | — | go through the document given by Sanket for the new requirement | —
98 | Punjab Flod\od - new requirement ticket creation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-12 | 2026-08-12 | 2026-08-12 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-163 https://cimcondigital.atlassian.net/browse/P4PFM-164 https://cimcondigital.atlassian.net/browse/P4PFM-165 https://cimcondigital.atlassian.net/browse/P4PFM-166 | — | —
99 | Punjab Flood monitoring - Backlog ticket closing | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-11 | 2026-08-11 | 2026-08-11 06:30 | -- All backlog tickets are closed. https://cimcondigital.atlassian.net/browse/P4PFM-8 https://cimcondigital.atlassian.net/browse/P4PFM-13 https://cimcondigital.atlassian.net/browse/P4PFM-18 https://cimcondigital.atlassian.net/browse/P4PFM-17 https://cimcondigital.atlassian.net/browse/P4PFM-16 https://cimcondigital.atlassian.net/browse/P4PFM-15 https://cimcondigital.atlassian.net/browse/P4PFM-12 https://cimcondigital.atlassian.net/browse/P4PFM-11 https://cimcondigital.atlassian.net/browse/P4PFM-9 https://cimcondigital.atlassian.net/browse/P4PFM-10 https://cimcondigital.atlassian.net/browse/P4PFM-14 https://cimcondigital.atlassian.net/browse/P4PFM-34 | — | —
100 | CIMtrack - Confluence Release note | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-11 | 2026-08-11 | 2026-08-11 06:30 | https://cimcondigital.atlassian.net/wiki/spaces/~712020701c30ec56b0488f85cefbc84dcd5395/pages/1823473667/Release+Notes+-+CIMTrack+-+CIMTrack+Dashboard+V1.6.0+-Sprint+4.1+-+Aug+11+10+48?atlOrigin=eyJpIjoiYzRmNzlmNWQyMjYwNGUxZmIxZTM0NmM4OGE0ZTU1MTMiLCJwIjoiYyJ9 | Create a confluence release note from the JIRA releases. | —
101 | CIMTrack - Release mail | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-11 | 2026-08-11 | 2026-08-11 06:30 | Mail sent to Afsana, Lokesh ji, Sandip sir, nisha ma'am, Jutan sir, Sanket and Rutvik. | Draft and sent the release mail to the higher management. | —
102 | Punjab - new requirement ticket creation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-11 | 2026-08-11 | 2026-08-11 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-153 https://cimcondigital.atlassian.net/browse/P4PFM-154 https://cimcondigital.atlassian.net/browse/P4PFM-155 https://cimcondigital.atlassian.net/browse/P4PFM-156 https://cimcondigital.atlassian.net/browse/P4PFM-157 https://cimcondigital.atlassian.net/browse/P4PFM-158 https://cimcondigital.atlassian.net/browse/P4PFM-159 https://cimcondigital.atlassian.net/browse/P4PFM-160 | 1. Device Name : Device name(e.g., AWLR 2047) should be shown below the site name (in small font size) 2. Dashboard Tiles (Tabs) : The following dashboard tiles should have the option to be shown or hidden as required: 3. In tile “Site status” detail page of high/medium/ low/normal site is not opening. 4. Manual Reading : In the Manual Reading Entry section, the Water Level field should support both Feet and Meter units for entering water-level readings. An Edit button should be provided for both Manual Readings and Sensor Readings, allowing authorized users to modify the recorded readings. 5. Reports & Analytics Module Access : If the Reports & Analytics module is disabled for a user from the Admin ID, the “Details” button should be removed from that user’s Sites table on the Dashboard. This is required because the Details page currently provides access to Reports and Export functionality. 6. Manual Alert Placement : Move the Manual Alert/SOS functionality from the Site Details page to the Dashboard. | —
103 | SWSM KT | SWSM | Done | Medium | Sanket Bhimani | 2026-08-10 | 2026-08-10 | 2026-08-10 06:30 | — | KT Session with Sanket | —
104 | CIMTrack dashboard release | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-10 | 2026-08-10 | 2026-08-10 06:30 | — | - Release note creation - Release mail - JIRA Release ticket management - Confluence management | —
105 | Punjab - RFQA ticket closing | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-10 | 2026-08-10 | 2026-08-10 06:30 | Closed : https://cimcondigital.atlassian.net/browse/P4PFM-146 https://cimcondigital.atlassian.net/browse/P4PFM-81 https://cimcondigital.atlassian.net/browse/P4PFM-116 https://cimcondigital.atlassian.net/browse/P4PFM-98 https://cimcondigital.atlassian.net/browse/P4PFM-91 https://cimcondigital.atlassian.net/browse/P4PFM-108 https://cimcondigital.atlassian.net/browse/P4PFM-112 https://cimcondigital.atlassian.net/browse/P4PFM-100 https://cimcondigital.atlassian.net/browse/P4PFM-124 https://cimcondigital.atlassian.net/browse/P4PFM-5 "https://cimcondigital.atlassian.net/browse/P4PFM-3 https://cimcondigital.atlassian.net/browse/P4PFM-42 "https://cimcondigital.atlassian.net/browse/P4PFM-7 https://cimcondigital.atlassian.net/browse/P4PFM-43 https://cimcondigital.atlassian.net/browse/P4PFM-6 https://cimcondigital.atlassian.net/browse/P4PFM-28 https://cimcondigital.atlassian.net/browse/P4PFM-151 https://cimcondigital.atlassian.net/browse/P4PFM-152 | close all the remaining tickets from the JIRA | —
106 | Deployment | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-10 | 2026-08-10 | 2026-08-10 06:30 | Deployment done in http://203.88.128.141:8443/ | Monitor the deployment of new requirements of the Punjab client. | —
107 | Ticket Creation - Punjab Flood project | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Nilesh Bhil | 2026-08-07 | 2026-08-07 | 2026-08-07 06:30 | I have created tickets for all the enhancement points which we received in previous week by client https://cimcondigital.atlassian.net/browse/P4PFM-113 https://cimcondigital.atlassian.net/browse/P4PFM-114 https://cimcondigital.atlassian.net/browse/P4PFM-115 https://cimcondigital.atlassian.net/browse/P4PFM-116 https://cimcondigital.atlassian.net/browse/P4PFM-117 https://cimcondigital.atlassian.net/browse/P4PFM-118 https://cimcondigital.atlassian.net/browse/P4PFM-119 https://cimcondigital.atlassian.net/browse/P4PFM-120 https://cimcondigital.atlassian.net/browse/P4PFM-121 https://cimcondigital.atlassian.net/browse/P4PFM-122 https://cimcondigital.atlassian.net/browse/P4PFM-123 https://cimcondigital.atlassian.net/browse/P4PFM-124 https://cimcondigital.atlassian.net/browse/P4PFM-125 https://cimcondigital.atlassian.net/browse/P4PFM-126 https://cimcondigital.atlassian.net/browse/P4PFM-127 https://cimcondigital.atlassian.net/browse/P4PFM-128 https://cimcondigital.atlassian.net/browse/P4PFM-129 https://cimcondigital.atlassian.net/browse/P4PFM-130 https://cimcondigital.atlassian.net/browse/P4PFM-131 https://cimcondigital.atlassian.net/browse/P4PFM-132 https://cimcondigital.atlassian.net/browse/P4PFM-133 https://cimcondigital.atlassian.net/browse/P4PFM-134 https://cimcondigital.atlassian.net/browse/P4PFM-135 https://cimcondigital.atlassian.net/browse/P4PFM-136 https://cimcondigital.atlassian.net/browse/P4PFM-137 https://cimcondigital.atlassian.net/browse/P4PFM-138 https://cimcondigital.atlassian.net/browse/P4PFM-139 https://cimcondigital.atlassian.net/browse/P4PFM-140 https://cimcondigital.atlassian.net/browse/P4PFM-141 https://cimcondigital.atlassian.net/browse/P4PFM-142 https://cimcondigital.atlassian.net/browse/P4PFM-143 https://cimcondigital.atlassian.net/browse/P4PFM-144 https://cimcondigital.atlassian.net/browse/P4PFM-145 https://cimcondigital.atlassian.net/browse/P4PFM-146 https://cimcondigital.atlassian.net/browse/P4PFM-147 https://cimcondigital.atlassian.net/browse/P4PFM-148 https://cimcondigital.atlassian.net/browse/P4PFM-149 https://cimcondigital.atlassian.net/browse/P4PFM-150 https://cimcondigital.atlassian.net/browse/P4PFM-151 https://cimcondigital.atlassian.net/browse/P4PFM-152 | create ticket of the client feedback and requirements. | —
108 | Resolve client queries and doubts | Punjab Flood Monitoring | Done | Medium | — | 2026-08-06 | 2026-08-06 | 2026-08-06 06:30 | 1. Sat with Sandip sir and discussed all the points and resolved them. 2. shared screen shot or each issue along with screen recording when needed. 3. prepared the word document with screenshot as proof. Issue : they did not perform the hard refresh so based on cookies previous data was showing. approx 1.5 hours | Rajnish sir shared the message to Sandip sir with points that enhancements are not done and there are issues in it. | —
109 | Punjab - VPN & server configuration | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-05 | 2026-08-05 | 2026-08-05 06:30 | — | — | —
110 | Punjab flood monitoring - new requirement validation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-05 | 2026-08-05 | 2026-08-06 06:30 | 1. Verified the mobile changes with Rutvik and understood the new requirements. 2. Verified 13/22 requirements of dashboard with harihar - 12:30PM 3. Verified other 5 requirements of dashboard with harihar - 4:30 PM | Verify Mobile application changes and dashboard changes. | —
111 | CIMTrack - RFQA ticket closing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-05 | 2026-08-06 | 2026-08-06 06:30 | https://cimcondigital.atlassian.net/browse/CIMTRACK-677 https://cimcondigital.atlassian.net/browse/CIMTRACK-719 https://cimcondigital.atlassian.net/browse/CIMTRACK-720 https://cimcondigital.atlassian.net/browse/CIMTRACK-721 https://cimcondigital.atlassian.net/browse/CIMTRACK-722 https://cimcondigital.atlassian.net/browse/CIMTRACK-723 https://cimcondigital.atlassian.net/browse/CIMTRACK-724 https://cimcondigital.atlassian.net/browse/CIMTRACK-728 https://cimcondigital.atlassian.net/browse/CIMTRACK-745 | https://cimcondigital.atlassian.net/browse/CIMTRACK-657 https://cimcondigital.atlassian.net/browse/CIMTRACK-677 https://cimcondigital.atlassian.net/browse/CIMTRACK-719 https://cimcondigital.atlassian.net/browse/CIMTRACK-720 https://cimcondigital.atlassian.net/browse/CIMTRACK-721 https://cimcondigital.atlassian.net/browse/CIMTRACK-722 https://cimcondigital.atlassian.net/browse/CIMTRACK-723 https://cimcondigital.atlassian.net/browse/CIMTRACK-724 https://cimcondigital.atlassian.net/browse/CIMTRACK-728 https://cimcondigital.atlassian.net/browse/CIMTRACK-745 | —
112 | NLC - Device configuration and command visibility | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-08-04 | 2026-08-04 | 2026-08-04 06:30 | Reconfigured the NLC Monitoring Dashboard after the local IP address change and updated the system configuration accordingly. Updated command settings and payload structure to align with the latest device communication format. Enhanced the monitoring dashboard to display commands sent from ThingsBoard to devices in real time. Configured the communication layer between the NLC Monitoring Dashboard and ThingsBoard for monitoring light status updates. Implemented an asynchronous device runner architecture with buffered batch updates to support scalable MQTT device monitoring. Implemented the Device History module to track and verify historical device events and telemetry. Added manual Device Connect and Disconnect functionality for testing and monitoring. Integrated compatibility for ThingsBoard Read Data commands within the monitoring dashboard. Implemented the core device simulation engine, MQTT connection management, and command handling architecture for the NLC simulator. (6 Hrs) | — | —
113 | Requirement go through | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Nilesh Bhil | 2026-08-04 | 2026-08-04 | 2026-08-04 06:30 | — | go through the requirements shared by the client. | —
114 | Punjab flood monitoring - service understanding | Punjab Flood Monitoring | Done | Medium | Nilesh Bhil | 2026-08-03 | 2026-08-03 | 2026-08-03 06:30 | Discussed and understood the working of notification and alert escalation services in the Punjab Flood Project with Nilesh bhai. | Discuss & understand the working services in the Punjab flood project for notification and alert escalation | —
115 | Punjab Flood - Task RFQA tickets | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-03 | 2026-08-03 | 2026-08-03 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-93 https://cimcondigital.atlassian.net/browse/P4PFM-101 https://cimcondigital.atlassian.net/browse/P4PFM-106 https://cimcondigital.atlassian.net/browse/P4PFM-102 https://cimcondigital.atlassian.net/browse/P4PFM-103 https://cimcondigital.atlassian.net/browse/P4PFM-110 https://cimcondigital.atlassian.net/browse/P4PFM-61 https://cimcondigital.atlassian.net/browse/P4PFM-27 https://cimcondigital.atlassian.net/browse/P4PFM-63 https://cimcondigital.atlassian.net/browse/P4PFM-104 - All tickets has been verified and closed with screenshots and screen recording where required. | https://cimcondigital.atlassian.net/browse/P4PFM-93 https://cimcondigital.atlassian.net/browse/P4PFM-101 https://cimcondigital.atlassian.net/browse/P4PFM-106 https://cimcondigital.atlassian.net/browse/P4PFM-102 https://cimcondigital.atlassian.net/browse/P4PFM-103 https://cimcondigital.atlassian.net/browse/P4PFM-110 https://cimcondigital.atlassian.net/browse/P4PFM-61 https://cimcondigital.atlassian.net/browse/P4PFM-27 https://cimcondigital.atlassian.net/browse/P4PFM-63 https://cimcondigital.atlassian.net/browse/P4PFM-104 | —
116 | CIMTrack - new sprint creation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-08-03 | 2026-08-03 | 2026-08-03 06:30 | — | create a new sprint for the backend release of DAR module. | —
117 | Ticket creation for identified points | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-08-01 | 2026-08-03 | 2026-08-03 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-107 https://cimcondigital.atlassian.net/browse/P4PFM-108 https://cimcondigital.atlassian.net/browse/P4PFM-109 https://cimcondigital.atlassian.net/browse/P4PFM-110 https://cimcondigital.atlassian.net/browse/P4PFM-111 https://cimcondigital.atlassian.net/browse/P4PFM-112 | — | —
118 | Punjab Flood Monitoring – Demo Release Testing and Validation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-01 | 2026-08-01 | 2026-08-03 06:30 | Conducted manual testing and verification for the client demo release. Performed sanity testing on the local IP and regression testing on the Demo IP to validate application functionality. Identified issues during testing and reported the relevant bugs to the development team for resolution. | Perform testing and validation activities for the client demo release to ensure application stability and verify that existing functionalities work as expected across different environments. | —
119 | Punjab Flood Monitoring – Universal User Role-Based Login Validation Automation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-08-01 | 2026-08-01 | 2026-08-01 06:30 | Created a universal automation script to validate role-based login for all existing user designations. The script dynamically identifies displayed designations, allowing it to support newly added or updated roles without any code changes or external dependencies. | Develop a universal automation script to validate role-based user login for all existing and future user designations. The script should dynamically adapt to updated roles without relying on hardcoded values or additional maintenance. | —
120 | Tender Ai manual verification after test cases | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-08-01 | 2026-08-01 | 2026-08-01 06:30 | — | — | —
121 | Tender AI - Test Cases | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-08-01 | 2026-08-01 | 2026-08-01 06:30 | — | — | —
122 | Default user password ticket closing | Punjab Flood Monitoring | Done | Medium | Nilesh Bhil | 2026-07-31 | 2026-08-01 | 2026-08-03 06:30 | Closed - https://cimcondigital.atlassian.net/browse/P4PFM-99 | https://cimcondigital.atlassian.net/browse/P4PFM-99 | —
123 | Punjab new RFQA ticket closing | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-31 | 2026-08-03 | 2026-08-03 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-78 https://cimcondigital.atlassian.net/browse/P4PFM-93 https://cimcondigital.atlassian.net/browse/P4PFM-101 https://cimcondigital.atlassian.net/browse/P4PFM-103 https://cimcondigital.atlassian.net/browse/P4PFM-106 | https://cimcondigital.atlassian.net/browse/P4PFM-78 https://cimcondigital.atlassian.net/browse/P4PFM-93 https://cimcondigital.atlassian.net/browse/P4PFM-102 https://cimcondigital.atlassian.net/browse/P4PFM-103 https://cimcondigital.atlassian.net/browse/P4PFM-106 | —
124 | Meeting with Sandip sir for Punjab project | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Nilesh Bhil | 2026-07-31 | 2026-07-31 | 2026-07-31 06:30 | 1 hour and 20 minutes of meeting done with Sandip sir, Harihar, Nilesh and Yash. | — | —
125 | CIMTrack DAR module ticket closing & test case updation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 | https://cimcondigital.atlassian.net/browse/CIMTRACK-694 Closed with test sheet attached. | close https://cimcondigital.atlassian.net/browse/CIMTRACK-694 ticket and update the test case sheet as well and attach in the ticket. | —
126 | Punjab - Close all RFQA tickets - Nilesh bhill | Punjab Flood Monitoring | Done | Medium | Nilesh Bhil | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-75 https://cimcondigital.atlassian.net/browse/P4PFM-77 https://cimcondigital.atlassian.net/browse/P4PFM-83 https://cimcondigital.atlassian.net/browse/P4PFM-84 https://cimcondigital.atlassian.net/browse/P4PFM-86 https://cimcondigital.atlassian.net/browse/P4PFM-89 https://cimcondigital.atlassian.net/browse/P4PFM-96 | https://cimcondigital.atlassian.net/browse/P4PFM-75 https://cimcondigital.atlassian.net/browse/P4PFM-77 https://cimcondigital.atlassian.net/browse/P4PFM-83 https://cimcondigital.atlassian.net/browse/P4PFM-84 https://cimcondigital.atlassian.net/browse/P4PFM-86 https://cimcondigital.atlassian.net/browse/P4PFM-89 https://cimcondigital.atlassian.net/browse/P4PFM-96 | —
127 | forgot password otp ticket. | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 | - Ticket created and assigned to Harihar : https://cimcondigital.atlassian.net/browse/P4PFM-104 | Create ticket for the correct message display in the modal. | —
128 | Punjab - Close all RFQA tickets - Harihar | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 | https://cimcondigital.atlassian.net/browse/P4PFM-79 https://cimcondigital.atlassian.net/browse/P4PFM-80 https://cimcondigital.atlassian.net/browse/P4PFM-82 https://cimcondigital.atlassian.net/browse/P4PFM-94 https://cimcondigital.atlassian.net/browse/P4PFM-95 https://cimcondigital.atlassian.net/browse/P4PFM-97 Closed all tickets with QC and screen recording or ss as required. | Close : https://cimcondigital.atlassian.net/browse/P4PFM-79 https://cimcondigital.atlassian.net/browse/P4PFM-80 https://cimcondigital.atlassian.net/browse/P4PFM-82 https://cimcondigital.atlassian.net/browse/P4PFM-94 https://cimcondigital.atlassian.net/browse/P4PFM-95 https://cimcondigital.atlassian.net/browse/P4PFM-97 | —
129 | CIMTrack - DAR RFQA Ticket closing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-30 | 2026-07-31 | 2026-07-31 06:30 | https://cimcondigital.atlassian.net/browse/CIMTRACK-740 https://cimcondigital.atlassian.net/browse/CIMTRACK-741 https://cimcondigital.atlassian.net/browse/CIMTRACK-742 https://cimcondigital.atlassian.net/browse/CIMTRACK-743 https://cimcondigital.atlassian.net/browse/CIMTRACK-744 Tickets closed with QC and screenshots and screen recording if required. | https://cimcondigital.atlassian.net/browse/CIMTRACK-740 https://cimcondigital.atlassian.net/browse/CIMTRACK-741 https://cimcondigital.atlassian.net/browse/CIMTRACK-742 https://cimcondigital.atlassian.net/browse/CIMTRACK-743 https://cimcondigital.atlassian.net/browse/CIMTRACK-744 Close this tickets. | —
130 | Create Punjab tickets | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-30 | 2026-07-30 | 2026-07-30 06:30 | Created JIRA tickets : https://cimcondigital.atlassian.net/browse/P4PFM-99 https://cimcondigital.atlassian.net/browse/P4PFM-100 https://cimcondigital.atlassian.net/browse/P4PFM-101 https://cimcondigital.atlassian.net/browse/P4PFM-102 | create tickets for the discussed points with harihar | —
131 | Role-Based Credential Verification | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Nilesh Bhil | 2026-07-30 | 2026-07-30 | 2026-07-30 06:30 | Completed manual testing of the dashboard for all current users on Harihar's local IP and on mobile devices, and created an automation script to verify dashboard access and user roles automatically. | Verify that all user credentials are working correctly according to their assigned roles and permissions. Check access for each role and identify any permission or login issues. | —
132 | Discussion with harihar | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-30 | 2026-07-30 | 2026-07-30 06:30 | task completed | Discussion with harihar regarding the issues | —
133 | CIMTrack ticket creation for DAR module | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-27 | 2026-07-30 | 2026-07-30 06:30 | Created JIRA tickets : https://cimcondigital.atlassian.net/browse/CIMTRACK-740 https://cimcondigital.atlassian.net/browse/CIMTRACK-741 https://cimcondigital.atlassian.net/browse/CIMTRACK-742 https://cimcondigital.atlassian.net/browse/CIMTRACK-743 https://cimcondigital.atlassian.net/browse/CIMTRACK-744 | create the DAR module ticket for the 5 points which were discovered during the testing | —
134 | Create Jira for the NLC issue of data loading hang | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-27 | 2026-07-30 | 2026-07-30 06:30 | task completed | — | —
135 | GMDA - Jal Mitra KT | GMDA - JAL Mitra | Done | Medium | Rutvik Panchal | 2026-07-06 | 2026-07-16 | 2026-07-28 06:30 | task completed | — | —
136 | CIMTrack - DAR Module dashboard testing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-28 | 2026-07-28 | 2026-07-28 06:30 | task completed | — | —
137 | NLC - Device connectivity issue root cause analysis | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-27 | 2026-07-27 | 2026-07-27 06:30 | task completed | — | —
138 | CIMTrack - Mobile UI Designing v2 | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-27 | 2026-07-28 | 2026-07-28 06:30 | task completed | Attendance Page, History page and User page. | —
139 | NLC - new 250 Device validation | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-24 | 2026-07-27 | 2026-07-27 06:30 | task completed | new devices are not able to send the data to thingsboard | System issue
140 | Punjab flood iOS testing | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-07-27 | 2026-07-27 | 2026-07-27 06:30 | task completed | — | —
141 | CIMTrack - DAR module dashboard testcase creation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-27 | 2026-07-27 | 2026-07-27 06:30 | task completed | — | —
142 | New 250 NLC Device configuration | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-24 | 2026-07-24 | 2026-07-24 06:30 | task completed | — | —
143 | CIMTrack - Mobile UI Designing | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-24 | 2026-07-24 | 2026-07-24 06:30 | task completed | Splash screen, Login page & Home page | —
144 | Weekly update to sandip sir | General Project | Done | Medium | — | 2026-07-22 | 2026-07-22 | 2026-07-22 06:30 | task completed | — | —
145 | User Guide screenshot uploading | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Rutvik Panchal, Nilesh Bhil | 2026-07-22 | 2026-08-07 | 2026-08-03 06:30 | — | — | —
146 | CIMTrack UI Redesign meeting | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-21 | 2026-07-21 | 2026-07-21 06:30 | task completed | conduct a meeting with farman and team for the new ui review and discussion | —
147 | PFM - RFQA ticket closing | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-07-20 | 2026-07-21 | 2026-07-21 06:30 | task completed | https://cimcondigital.atlassian.net/browse/P4PFM-73 https://cimcondigital.atlassian.net/browse/P4PFM-74 https://cimcondigital.atlassian.net/browse/P4PFM-85 https://cimcondigital.atlassian.net/browse/P4PFM-87 https://cimcondigital.atlassian.net/browse/P4PFM-88 https://cimcondigital.atlassian.net/browse/P4PFM-90 | —
148 | PFM - Web Dashboard testing | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay, Nilesh Bhil | 2026-07-20 | 2026-07-25 | 2026-07-27 06:30 | task completed | i have stopped the testing as UT wasn't done by developer | —
149 | PFM - Mobile application testing | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-07-20 | 2026-07-21 | 2026-07-20 06:30 | task completed | — | —
150 | CIMTrack Ticket closing | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-20 | 2026-08-01 | 2026-08-03 06:30 | 1. Closed - https://cimcondigital.atlassian.net/browse/CIMTRACK-698 2. Closed - https://cimcondigital.atlassian.net/browse/CIMTRACK-718 | https://cimcondigital.atlassian.net/browse/CIMTRACK-698 https://cimcondigital.atlassian.net/browse/CIMTRACK-718 | —
151 | Savio - ticket creation | Savio | Done | Medium | Dev Patel | 2026-07-18 | 2026-07-18 | 2026-07-18 06:30 | task completed | create ticket for all the points given by dev for improvements and bugs | —
152 | Punjab flood mobile test cases creation | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-18 | 2026-07-21 | 2026-07-20 06:30 | task completed | It will take upto 5-6 hours | —
153 | Punjab Flood - Dashboard KT | Punjab Flood Monitoring | Done | Medium | Harihar Upadhyay | 2026-07-18 | 2026-07-18 | 2026-07-18 06:30 | task completed | — | —
154 | Punjab Flood - Mobile KT | Punjab Flood Monitoring | Done | Medium | Rutvik Panchal | 2026-07-17 | 2026-07-17 | 2026-07-17 06:30 | task completed | — | —
155 | NLC - Multi Device upload | NLC Dashboard (Network light control system) | Done | High | Jil Shah | 2026-07-16 | 2026-07-16 | 2026-07-16 06:30 | task completed | — | —
156 | NLC - Multi Devices configuration | NLC Dashboard (Network light control system) | Done | High | Jil Shah | 2026-07-16 | 2026-07-17 | 2026-07-17 06:30 | task completed | create a playwright script to configure the credentials in thingsboard NLC | —
157 | NLC - Ticket closing | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-16 |  | 2026-09-01 06:30 | — | — | —
158 | NLC -Monitoring Dashboard creation | NLC Dashboard (Network light control system) | Done | High | Jil Shah | 2026-07-15 | 2026-07-18 | 2026-07-17 06:30 | task completed | — | —
159 | AI360 discussion | General Project | Done | Low | — | 2026-07-15 | 2026-07-15 | 2026-07-15 06:30 | task completed | Discussion with sandip sir and AI-ML team. | —
160 | NLC - Load testing script creation | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-15 | 2026-07-20 | 2026-07-15 06:30 | task completed | — | —
161 | NLC - Load testing planning | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-07-14 | 2026-07-14 | 2026-07-14 06:30 | task completed | — | —
162 | CIMTrack Redesign meeting | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-13 | 2026-07-13 | 2026-07-13 06:30 | task completed | — | —
163 | Create JIRA Tickets | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-10 | 2026-07-10 | 2026-07-10 06:30 | task completed | Jira tickets for the points suggested by Lokesh ji and Jutan sir. | —
164 | CIMTrack sprint 4 planning | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-09 | 2026-07-09 | 2026-07-09 06:30 | task completed | — | —
165 | CIMTrack Ticket creation | CIMTrack Dashboard, CIMTrack | Done | Medium | Sanket Bhimani, Rutvik Panchal | 2026-07-09 | 2026-07-09 | 2026-07-09 06:30 | task completed | Create tickets for the remaining points of sprint 4 | —
166 | T360 Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-07-08 | 2026-07-10 | 2026-07-09 06:30 | task completed | https://cimcondigital.atlassian.net/browse/T3-118 https://cimcondigital.atlassian.net/browse/T3-137 https://cimcondigital.atlassian.net/browse/T3-138 https://cimcondigital.atlassian.net/browse/T3-128 https://cimcondigital.atlassian.net/browse/T3-140 https://cimcondigital.atlassian.net/browse/T3-141 https://cimcondigital.atlassian.net/browse/T3-142 https://cimcondigital.atlassian.net/browse/T3-143 https://cimcondigital.atlassian.net/browse/T3-139 | —
167 | TSA Meeting | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-07-08 | 2026-07-08 | 2026-07-08 06:30 | task completed | — | —
168 | CIMTrack Dashboard V1.5 Release Note JIRA | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-07 | 2026-07-07 | 2026-07-07 06:30 | task completed | — | —
169 | CIMTrack Dashboard V1.5.0 Release | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-07 | 2026-07-07 | 2026-07-07 06:30 | task completed | — | —
170 | Onboardify - User Guide Creation | onboardify 2.0 | Done | Medium | — | 2026-07-06 | 2026-07-11 | 2026-07-08 06:30 | task completed | — | —
171 | Tender360 - Feedback ticket generation | Tender 360 | Done | Medium | Dev Patel | 2026-07-06 | 2026-07-07 | 2026-07-07 06:30 | task completed | — | —
172 | Create Jira Ticket | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-06 | 2026-07-06 | 2026-07-06 06:30 | task completed | The following changes have been implemented: 1. In Voucher Approval, under the Conveyance - 2 Wheeler and Conveyance - 4 Wheeler voucher sections, the CIMTrack Calculated KM and Route columns have been removed. Only the Claim KM column is now displayed. 2. The Expense Head-wise Grouping feature has been implemented and is now available within the Expense Head Summary accordion. 3. A filter has also been added to the Expense Head column in the Line Items section to make it easier to filter and review expense records. | —
173 | CIMTrack Release Ticket closing | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-04 | 2026-07-04 | 2026-07-04 06:30 | task completed | — | —
174 | Sales Automation overview | General Project | Done | Medium | — | 2026-07-03 |  | 2026-08-18 06:30 | Yash left CIMCON | — | —
175 | refactor CIMTrack JIRA Completely | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-04 | 2026-07-03 06:30 | task completed | — | —
176 | Tender360 Release note preparation | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30 | task completed | — | —
177 | Tender360 Release points preparation | Tender 360 | Done | Medium | Dev Patel | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30 | task completed | — | —
178 | CIMTrack Release note & mail preparation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-03 | 2026-07-03 | 2026-07-03 06:30 | task completed | — | —
179 | Tender360 - Close the remaining topic | Tender 360 | Done | Medium | Dev Patel | 2026-07-02 | 2026-07-02 | 2026-07-02 06:30 | task completed | — | —
180 | GMDA - Jal Mitra Test Cases creation | GMDA - JAL Mitra | To-Do | Low | Rutvik Panchal | 2026-07-06 | 2026-07-24 |  | — | — | —
181 | Create ticket for the file upload Mandatory for the daily activity report. | CIMTrack | Done | Medium | Rutvik Panchal | 2026-07-02 | 2026-07-02 | 2026-07-02 06:30 | task completed | — | —
182 | CIMTrack PM Dashboard Release note creation | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-02 | 2026-07-04 | 2026-07-03 06:30 | task completed | — | —
183 | CIMTrack - PM Dashboard Testing | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-07-01 | 2026-07-01 | 2026-07-01 06:30 | task completed | — | —
184 | NLC - Manual Testing and Data validation | NLC Dashboard (Network light control system) | Done | Low | Jil Shah | 2026-07-01 |  | 2026-09-01 06:30 | — | — | —
185 | CMS - bifurcate the test types file strcuture. | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-30 | 2026-06-30 | 2026-06-30 06:30 | task completed | — | —
186 | CMS - Smoke Testing bifurcation in automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-29 | 2026-06-29 | 2026-06-29 06:30 | task completed | — | —
187 | NLC KT | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-06-27 | 2026-06-27 | 2026-06-27 06:30 | task completed | — | —
188 | Tender360 - Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-30 |  | 2026-07-02 06:30 | task completed | https://cimcondigital.atlassian.net/browse/T3-124 https://cimcondigital.atlassian.net/browse/T3-127 https://cimcondigital.atlassian.net/browse/T3-132 https://cimcondigital.atlassian.net/browse/T3-134 | —
189 | CMS - User Management Filter Automation & Validation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-29 | 2026-06-26 06:30 | task completed | — | —
190 | CMS - Impersonate user Automation flow & Validation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-29 | 2026-06-26 06:30 | task completed | — | —
191 | CMS - Edit User Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30 | task completed | — | —
192 | CMS - User Deactivation Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30 | task completed | — | —
193 | Tender360 - Ticket creation | Tender 360 | Done | Medium | Dev Patel | 2026-06-25 | 2026-06-26 | 2026-06-26 06:30 | task completed | Create the tickets after the meeting with Komal ma'am and sandip sir. | —
194 | CMS - User Set up Automation flow | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-29 06:30 | task completed | — | —
195 | CMS - User Activation Flow automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-26 | 2026-06-26 | 2026-06-26 06:30 | task completed | — | —
196 | NLC - KT | NLC Dashboard (Network light control system) | Done | Medium | Jil Shah | 2026-06-25 | 2026-06-25 | 2026-06-25 06:30 | task completed | — | —
197 | CMS - Load testing setup | CMS - Urban Voice | Done | Medium | — | 2026-06-11 | 2026-06-12 | 2026-06-12 06:30 | task completed | — | —
198 | Onboardify KT & Project Discussion | onboardify 2.0 | Done | Low | — | 2026-06-24 | 2026-06-24 | 2026-06-25 05:04 | task completed | — | —
199 | UrbanVoice - Home page | CMS - Urban Voice | Done | Low | Harihar Upadhyay | 2026-06-24 | 2026-06-26 | 2026-06-26 06:30 | task completed | Enhance the front-end | —
200 | Tender360 v2.4.3 KT Meeting | Tender 360 | Done | Medium | Dev Patel | 2026-06-24 | 2026-06-24 |  | task completed | — | —
201 | Tender360 - 4 Hours Threshold Ticket Creationg | Tender 360 | Done | Medium | Dev Patel | 2026-06-24 | 2026-06-24 |  | task completed | — | —
202 | Punjab Flood Monitoring Meeting MOM | Punjab Flood Monitoring | Done | Medium | — | 2026-06-23 | 2026-06-23 |  | task completed | — | —
203 | Tender360 V2.4.3 Release | Tender 360 | Done | Medium | Dev Patel | 2026-06-23 | 2026-06-23 |  | task completed | — | —
204 | Tender360 - Script Enhancement | Tender 360 | Done | Medium | Dev Patel | 2026-06-23 |  | 2026-07-13 06:30 | task completed | — | —
205 | Tender360 Ticket Closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-22 | 2026-06-23 |  | task completed | https://cimcondigital.atlassian.net/browse/T3-113 https://cimcondigital.atlassian.net/browse/T3-116 https://cimcondigital.atlassian.net/browse/T3-104 https://cimcondigital.atlassian.net/browse/T3-114 https://cimcondigital.atlassian.net/browse/T3-115 https://cimcondigital.atlassian.net/browse/T3-108 | —
206 | Tender Automation - Ticket Creation | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-22 | 2026-06-22 |  | task completed | 1. Tender Documents – I have re-uploaded the tender documents. The financial document selection is now correct as per my last observation. However, there is still an issue with the fillable forms — the tool is currently preparing a single form for multiple tender forms. This needs to be resolved at the earliest. 2. Next Upgrade – Experience Document Selection Moving forward, the next enhancement involves the selection of experience documents within the tool. As discussed with both of you, kindly incorporate a toggle-type bar for the following sectors: - Water - Oil & Gas (O&G) - Lighting 3. Document Source – OneDrive Integration The selection of documents should be fetched directly from OneDrive (not from a local server), so that we can use and prepare the documents remotely as needed. | —
207 | CIMTrack Travel Script Test after production release | CIMTrack Dashboard | Done | Medium | Sanket Bhimani | 2026-06-22 | 2026-06-23 |  | task completed | Please check satya Prakash baghel and kapil dev nigam last 2 days comparison needed for actual travel and our script calculated travel | —
208 | CMS - Ticket Closing | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-19 | 2026-06-20 |  | task completed | — | —
209 | TSA - Final Bid grouping testing | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-19 | 2026-06-25 | 2026-06-25 06:30 | task completed | https://cimcondigital.atlassian.net/browse/TSA-39 | —
210 | Tender360 - Ticket closing | Tender 360 | Done | Medium | Dev Patel | 2026-06-19 | 2026-06-19 |  | task completed | https://cimcondigital.atlassian.net/browse/T3-110 https://cimcondigital.atlassian.net/browse/T3-104 https://cimcondigital.atlassian.net/browse/T3-115 https://cimcondigital.atlassian.net/browse/T3-100 https://cimcondigital.atlassian.net/browse/T3-111 https://cimcondigital.atlassian.net/browse/T3-112 https://cimcondigital.atlassian.net/browse/T3-107 | —
211 | Tender360 - Corrigendum Documents | Tender 360 | Done | Medium | Dev Patel | 2026-06-18 | 2026-06-18 |  | task completed | https://cimcondigital.atlassian.net/browse/T3-108 | —
212 | CMS - User Management Automation | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-17 |  | 2026-06-25 06:30 | task completed | — | —
213 | Tender360 - New ticket creation for the requirements. | Tender 360 | Done | High | Dev Patel | 2026-06-17 | 2026-06-17 |  | task completed | 1.AOC- winners list 2.prompt - admin control dynamic prompt(setting) 3.status - accept for bidding 4. notification | —
214 | Tender 360 - Ticket Closing | Tender 360 | Done | Urgent | Dev Patel | 2026-06-17 | 2026-06-17 |  | task completed | https://cimcondigital.atlassian.net/browse/T3-85 https://cimcondigital.atlassian.net/browse/T3-109 https://cimcondigital.atlassian.net/browse/T3-106 https://cimcondigital.atlassian.net/browse/T3-102 https://cimcondigital.atlassian.net/browse/T3-104 | —
215 | CMS - Production Release | CMS - Urban Voice | Done | High | Harihar Upadhyay | 2026-06-12 |  | 2026-07-13 06:30 | task completed | — | —
216 | Tender360 - Tender scrapping script initial enhancement | Tender 360 | Done | Medium | Dev Patel | 2026-06-12 | 2026-06-12 |  | task completed | — | —
217 | CMS - Initial Login load testing set up | CMS - Urban Voice | Done | Medium | Harihar Upadhyay | 2026-06-12 | 2026-07-13 | 2026-07-13 06:30 | task completed | — | —
218 | CIMTrack - Geo Tag Testing | CIMTrack | Done | Medium | Rutvik Panchal | 2026-06-03 | 2026-06-04 |  | task completed | https://cimcondigital.atlassian.net/browse/CIMTRACK-687 | —
219 | TSA - Tickets creation | Tender Submission Automation | Done | Medium | Viraj Soni | 2026-06-10 | 2026-06-10 |  | task completed | create ticket for the tickets / points | —
220 | CIMTrack - give discussion points | CIMTrack | Done | Medium | Rutvik Panchal | 2026-06-10 | 2026-06-10 |  | task completed | — | —
221 | Tender360 - Ticket creation | Tender 360 | Done | Medium | Dev Patel | 2026-06-10 | 2026-06-10 |  | task completed | Create all tickets discussed with the himanshu | —
222 | CIMTrack - Data Migration Validation | CIMTrack Dashboard | Done | Urgent | Sanket Bhimani | 2026-06-06 | 2026-06-06 |  | task completed | — | —
223 | CMS 2.0 - Iteration 2 Testing | CMS - Urban Voice | Done | Urgent | Harihar Upadhyay | 2026-06-05 | 2026-06-10 |  | task completed | — | —
224 | Tender360 - Discovered Tender page Testing | Tender 360 | Done | — | Dev Patel | 2026-06-05 | 2026-06-05 |  | task completed | — | —
225 | Tender360 - Discovered Tender Page Test Case writting | Tender 360 | Done | — | Dev Patel | 2026-06-05 | 2026-06-05 |  | task completed | — | —
226 | Onboardify - Positive Testing | Tender Submission Automation | Done | — | Viraj Soni | 2026-06-03 | 2026-06-06 |  | task completed | — | —
227 | Tender 360 - OCR Testing | Tender 360 | Done | Medium | Dev Patel | 2026-06-02 | 2026-06-05 |  | task completed | https://cimcondigital.atlassian.net/browse/T3-76 | —
228 | CIMTrack New Build Test | CIMTrack | Done | Low | Rutvik Panchal | 2026-05-30 | 2026-06-10 |  | task completed | 1. mime type change ( should be able to share on teams ) 2. New Message display for multiple try to check-in & check-out ( you have reached your limit message removed) | —
229 | CIMTrack - 672 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-29 | 2026-06-03 |  | task completed | https://cimcondigital.atlassian.net/browse/CIMTRACK-672 | —
230 | GMDA Testing & Release | WebScanet - GMDA | Done | Medium | — | 2026-05-29 |  | 2026-08-11 06:30 | — | — | —
231 | Parvati - iOS testing | Parvati Application | Done | — | Prakash Patel | 2026-05-28 | 2026-05-29 |  | task completed | — | —
232 | CIMTrack - Distance Script Testing | CIMTrack Dashboard | Done | — | Sanket Bhimani | 2026-05-27 | 2026-06-09 |  | task completed | — | —
233 | CIMTrack - 683 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-29 |  | task completed | https://cimcondigital.atlassian.net/browse/CIMTRACK-683 | —
234 | CIMTrack - 682 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-29 |  | task completed | https://cimcondigital.atlassian.net/browse/CIMTRACK-682 | —
235 | CIMTrack - 679 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-27 |  | task completed | https://cimcondigital.atlassian.net/browse/CIMTRACK-679?atlOrigin=eyJpIjoiMjc0YjExOGU1MThhNDliNWI1ZjEyMTk1NGRjYzM4ZWEiLCJwIjoiaiJ9 | —
236 | CIMTrack 678 | CIMTrack | Done | — | Rutvik Panchal | 2026-05-27 | 2026-05-27 |  | task completed | https://cimcondigital.atlassian.net/browse/CIMTRACK-678?atlOrigin=eyJpIjoiNGE5NDRkY2ViZjliNDc0OWI4NDFkNjM5NWI4MjMyNWYiLCJwIjoiaiJ9 | —
237 | Parvati iOS Testing | Parvati Application | Done | — | Prakash Patel | 2026-05-27 | 2026-05-29 |  | task completed | — | —
238 | Onboadify KT | onboardify 2.0 | Done | — | — | 2026-05-27 | 2026-05-27 |  | task completed | — | —
239 | CIMTrack Force Password Change | CIMTrack | Done | — | Rutvik Panchal | 2026-05-25 | 2026-05-29 |  | task completed | — | —
240 | CIMTrack Forgot Password Testing | CIMTrack | Done | — | — | 2026-05-25 | 2026-05-29 |  | task completed | — | —
241 | CIMTrack Battery Consumption optimization test | CIMTrack | Done | — | — | 2026-05-25 | 2026-06-01 |  | task completed | Test this for a week with different scenario | —
242 | TSA all tickets in RFQA | Tender Submission Automation | Done | — | — | 2026-05-20 | 2026-05-29 |  | task completed | should be able to complete this week or next week. | —
243 | CIMTrack Ticket verification | CIMTrack | Done | — | — | 2026-05-25 | 2026-05-29 |  | task completed | — | —
244 | CIMTrack previous Jira Ticket Resolutions | CIMTrack Dashboard | Done | — | — | 2026-05-16 | 2026-05-23 |  | task completed | https://cimcondigital.atlassian.net/browse/CIMTRACK-594 https://cimcondigital.atlassian.net/browse/CIMTRACK-57 https://cimcondigital.atlassian.net/browse/CIMTRACK-82 https://cimcondigital.atlassian.net/browse/CIMTRACK-106 https://cimcondigital.atlassian.net/browse/CIMTRACK-109 https://cimcondigital.atlassian.net/browse/CIMTRACK-119 https://cimcondigital.atlassian.net/browse/CIMTRACK-121 https://cimcondigital.atlassian.net/browse/CIMTRACK-122 https://cimcondigital.atlassian.net/browse/CIMTRACK-124 https://cimcondigital.atlassian.net/browse/CIMTRACK-125 https://cimcondigital.atlassian.net/browse/CIMTRACK-127 https://cimcondigital.atlassian.net/browse/CIMTRACK-134 https://cimcondigital.atlassian.net/browse/CIMTRACK-141 https://cimcondigital.atlassian.net/browse/CIMTRACK-142 https://cimcondigital.atlassian.net/browse/CIMTRACK-347 https://cimcondigital.atlassian.net/browse/CIMTRACK-348 https://cimcondigital.atlassian.net/browse/CIMTRACK-350 https://cimcondigital.atlassian.net/browse/CIMTRACK-366 https://cimcondigital.atlassian.net/browse/CIMTRACK-370 https://cimcondigital.atlassian.net/browse/CIMTRACK-371 https://cimcondigital.atlassian.net/browse/CIMTRACK-372 https://cimcondigital.atlassian.net/browse/CIMTRACK-378 https://cimcondigital.atlassian.net/browse/CIMTRACK-379 https://cimcondigital.atlassian.net/browse/CIMTRACK-380 https://cimcondigital.atlassian.net/browse/CIMTRACK-397 https://cimcondigital.atlassian.net/browse/CIMTRACK-398 https://cimcondigital.atlassian.net/browse/CIMTRACK-402 | —
245 | Test the Expense Voucher Flow | CIMTrack Dashboard | Done | — | — | 2026-05-15 | 2026-06-12 |  | task completed | Total 264 Test cases are done, now test it. | —

## Releases
Manual Releases — Total: 9
# | Release Name | Project(s) | Version(s) | Status | Release Date | Manager | Developers
1 | CIMTrack Sprint 4.1 | CIMTrack Dashboard | v1.6 | Released | 2026-08-11 | Dwip Pandya | Sanket Bhimani
2 | Tender360 - V2.4.5 | Tender 360 | V2.4.5 | Released | 2026-07-09 | Dwip Pandya | Dev Patel
3 | Tender360 - V2.4.4 | Tender 360 | V2.4.4 | Released | 2026-07-03 | Dwip Pandya | Dev Patel
4 | CIMTrack DAR Release | CIMTrack Dashboard | v1.5 | Released | 2026-07-07 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
5 | TSA V2.5.4 | Tender Submission Automation | V2.5.4 | Released | 2026-06-17 | Dwip Pandya | Viraj Soni
6 | Tender 360 Final Release | Tender 360 | V2.4.3 | Released | 2026-06-23 | Dwip Pandya | Dev Patel
7 | CIMTrack Sprint 3 - iOS | CIMTrack | V1.3.5 | Released | 2026-06-16 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
8 | CIMTrack Sprint 3 - Android | CIMTrack | v1.7.1 | Released | 2026-06-16 | Dwip Pandya | Sanket Bhimani, Rutvik Panchal
9 | Parvati Release | Parvati Application | V1.0.0 | Released | 2026-06-02 | Dwip Pandya | Prakash Patel
Release Points — Total: 7
# | Release Point Title | Project(s) | Type | Version(s) | Checklist Progress | Completed
1 | CIMTrack - Sprint 4.1 | CIMTrack Dashboard | Past | — | 18 / 18 items (100%) | Yes
2 | T360 - V2.4.6 | Tender 360 | Past | V2.4.5 (Prev) | 11 / 11 items (100%) | Yes
3 | CIMTrack - DAR Report | CIMTrack Dashboard, CIMTrack | Past | — | 11 / 11 items (100%) | Yes
4 | Tender360 V2.4.4 | Tender 360 | Past | V2.4.4 (Up) | 11 / 11 items (100%) | Yes
5 | TSA V2.2.4 Release | Tender Submission Automation | Past | V2.2.4 (Prev) | 10 / 10 items (100%) | Yes
6 | Tender 360 Final Release | Tender 360 | Past | V2.4.3 (Prev) | 20 / 20 items (100%) | Yes
7 | CIMTrack Sprint 3 | CIMTrack | Past | Android v1.7.1 (Prev), iOS V1.3.5 (Prev) | 15 / 15 items (100%) | Yes

## Test Cases
Test Case Counts by Project
# | Project | Total Test Cases | Not executed | Passed | Failed | Blocked
1 | CIMTrack Dashboard | 765 | 0 | 724 | 41 | 0
2 | CIMTrack | 148 | 0 | 147 | 1 | 0
3 | Purchase Module | 143 | 0 | 143 | 0 | 0
4 | Punjab Flood Monitoring | 125 | 0 | 123 | 1 | 1
5 | SWSM | 0 | 0 | 0 | 0 | 0
6 | General Project | 0 | 0 | 0 | 0 | 0
7 | Savio | 0 | 0 | 0 | 0 | 0
8 | GMDA - JAL Mitra | 0 | 0 | 0 | 0 | 0
9 | NLC Dashboard (Network light control system) | 0 | 0 | 0 | 0 | 0
10 | Engineering Document | 0 | 0 | 0 | 0 | 0
11 | WebScanet - GMDA | 60 | 0 | 57 | 3 | 0
12 | onboardify 2.0 | 0 | 0 | 0 | 0 | 0
13 | Tender 360 | 60 | 0 | 60 | 0 | 0
14 | Parvati Application | 116 | 0 | 99 | 17 | 0
15 | Tender Submission Automation | 383 | 0 | 383 | 0 | 0
16 | CMS - Urban Voice | 277 | 0 | 248 | 28 | 1
| TOTAL | 2077 | 0 | 1984 | 91 | 2
By Priority
# | Priority | Count
1 | Critical | 0
2 | High | 1246
3 | Medium | 761
4 | Low | 70
By Type
# | Type | Count
1 | Manual | 2008
2 | Automated | 0
3 | API | 0
4 | Security | 47
5 | Performance | 12
6 | Regression | 10